## 2025 Project Update
CoA Department | Year | Grant# | Informal Project Name | Grant Name | State Grant Amount | State Grant Amount Remaining | % Encumbered | Project Update | Reversion Date | Agreement Received
Parks & Recreation | 2022 | G2645 | 4-H Park | ALB 4-H PARK MEMORIAL REN | 50000 | 26130.58 | 47.74% | ​Quote and NoO to be requested following public meetings November 2024. | 6/30/2026 | 9/7/2022
Municipal Development | 2023 | H4027 | 4th St. NW | Fourth Street NW Improvements - Expand Purpose - Extend Time | 85000 | 85000 | 0% | ​Pending scope and fee from consultant due 12/01/24. Once received NOO to be submitted to NMDOT. Will be fully encumbered by 12/15/24 | 6/30/2025 | Received
Municipal Development | 2021 | F2974 | 98th and Unser Traffic Signal | ALB 98TH & UNSER TRAFFIC SIGNAL CONSTRUCT | 50000 | 998 | 98% | ​Awaiting reimbursement from NMDOT, requested since June 2024. Work completed. | 6/30/2025 | Received
Municipal Development | 2022 | G3106 | Academy & Wyoming | ACADEMY RD NE & WYOMING BLVD NE REPAIR | 25000 | 0 | 100% | Fully encumbered, Vehicle ordered pending delivery. | 6/30/2026 | Received
Albuquerque Community Safety | 2021 | F2650 | ACS Facility | ALB SAN MATEO SAFETY DEVELOPMENT CONSTRUCT | 100000 | 0 | 100% | ​Fully expended, project complete. | 6/30/2025 | 9/9/2021
Albuquerque Community Safety | 2022 | G2731 | ACS Facility | ALB RGNL PUBLIC SAFETY CTR IMPROVE | 2970000 | 0 | 100% | ​Fully expended, project complete. | 6/30/2026 | 9/2/2022
Albuquerque Community Safety | 2024 | I2722 | ACS Facility | ALB CMTY SAFETY FCLTY CONSTRUCT | 100000 | 22537.4 | 77.46% | ​Fencing being installed. HAWK signal in design, construction of which will encumber remaining funds once complete. | 6/30/2028 | 9/9/2024
Health, Housing, & Homelessness - NPO | 2023 | H2783 | Adelante NPO | VEHS & EQUIP PRCHS | 311490 | 311490 | Agreement not received from State | Waiting on Grant Agreement from State. | 6/30/2027
Health, Housing, & Homelessness - NPO | 2024 | I2726 | Adelante NPO | ALB DISAVANTAGED POPULATIONS EQUIP PRCHS | 160000 | 160000 | 0% | Waiting for contract exhibits from non-profit for Use Agreement to meet anti-Donation. | 6/30/2026 | 9/6/2024
Health, Housing, & Homelessness | 2022 | G2647 | Affordable Housing | ALB AFFORDABLE HOUSING CONSTRUCT | 455000 | 455000 | 0% | RFP will be issued December 2024. | 6/30/2026 | 2/27/2023
Health, Housing, & Homelessness | 2023 | H2784 | Affordable Housing | AFFORDABLE HOUSING CONSTRUCT | 1050202 | 1050202 | 0% | RFP will be issued December 2024. | 6/30/2027 | 10/31/2023
Health, Housing, & Homelessness | 2024 | I2699 | Affordable Housing | AFFORDABLE HSING CONSTRUCT | 780000 | 780000 | 0% | RFP will be issued December 2024. | 6/30/2028 | 10/1/2024
Health, Housing, & Homelessness - NPO | 2021 | F2577 | Affordable Housing AHA NPO | ALB AFFORDABLE HSING CONSTRUCT | 1600000 | 0 | 100% | ​Project has been completed and encumbered. | 6/30/2025 | 4/17/2023
Health, Housing, & Homelessness - NPO | 2023 | H2787 | Affordable Housing AHA NPO | AHA HSING IMPROVE | 150000 | 150000 | 0% | These are pass through funds with an already executed IGA. | 6/30/2027 | Received
Health, Housing, & Homelessness - NPO | 2024 | I2701 | Affordable Housing AHA NPO | AHA HSING CONSTRUCT | 250000 | 250000 | 0% | As of 10/8/2024, project has been allocated to Albuquerque Housing Authority. | 6/30/2028 | 10/1/2024
Health, Housing, & Homelessness | 2024 | I2698 | Affordable Housing MRG Housing Collaborative Construct | AFFORDABLE COLLABORATIVE HSING CONSTRUCT | 1100000 | 1100000 | 0% | As of 10/8/2024, an RFP has been released and closed. The submittals are now going through evaluations. | 6/30/2028 | 10/1/2024
Albuquerque Fire Rescue | 2023 | H2867 | AFR Apparatus | RESCUE VEHICLES PRCHS | 25000 | 0 | 100% | ​Project complete. Rescue Boat Purchased. | 6/30/2025 | 12/8/2023
Albuquerque Fire Rescue | 2023 | H4032 | AFR Apparatus | Fire Department Vehicle Purchase - Extend Time | 1190103 | 0 | 100% | ​Project complete. Funding was used for LIfePak 15's, E317 replacement brush truck and partial funding for new ladder. | 6/30/2025 | 9/15/2023
Albuquerque Fire Rescue | 2023 | H2820 | AFR Apparatus | FIRE RESCUE WATER RESCUE VEH PRCHS | 100000 | 236 | 99.76% | ​Vehicle Purchased and invoice paid | 6/30/2025 | 10/11/2023
Albuquerque Fire Rescue | 2023 | H2834 | AFR Apparatus | LADDER TRUCKS PRCHS | 92778 | 92778 | 0% | ​Waiting on reauthorization and change of scope to use the funding for FS 7 ladder equipment. Not enough funding to purchase a ladder. | 6/30/2025 | 10/11/2023
Albuquerque Fire Rescue | 2024 | I2738 | AFR Apparatus | ALB FIRE RESCUE APPARATUS PRCHS | 100000 | 100000 | 0% | ​Quote obtained but working on PO for partial funding of a Rescue (remaining funds will come from CDBG funds). Waiting for a funding string from department for CDBG funds. Expected delivery date for Rescue is 18 months after PO is created. | 6/30/2026 | 9/12/2024
Albuquerque Fire Rescue | 2023 | H2819 | AFR Equipment | FIRE RESCUE DEPT EMS EQUIP PRCHS | 440000 | 220269.92 | 49.94% | ​Total encumbered as of 10/15/2024 $219,730.08. Remaining funds will be spent by 10/30/25 due to staggered replacement plan on EMS equipment. | 6/30/2025 | 10/11/2023
Albuquerque Fire Rescue | 2023 | H2897 | AFR Equipment - UTV | WILDLAND FIREFIGHTING EQUIP PRCHS | 90000 | 0 | 100% | PO #FIR001922 obtained on 11/7/2024 from Siddons Martin. UTV will likely take 6 to 12 months to receive. | 6/30/2025 | 10/11/2023
Albuquerque Fire Rescue | 2024 | I2703 | AFR Equipment - UTV | ALB ALL-TERRAIN VEH PRCHS | 40000 | 0 | 100% | ​PO #FIR001922 obtained on 11/7/2024 from Siddons Martin. UTV will likely take 6 to 12 months to receive. | 6/30/2026 | 9/12/2024
Albuquerque Fire Rescue | 2024 | I2715 | AFR Equipment - UTV | ALB BRUSH TRUCK VEH PRCHS | 60000 | 60000 | 0% | ​NOO denied by DFA - obtaining new quotes from vendor. | 6/30/2026 | 9/12/2024
Albuquerque Fire Rescue | 2024 | I2741 | AFR Separate Sleeping Quarters | FIRE STN REN | 2634900 | 2634900 | 0% | ​In the process of acquiring an architect through DMD. This funding is remodel bunk rooms at five separate stations. | 6/30/2028 | 8/3/2024
Arts & Culture | 2022 | G2648 | African American Museum - CABQ | ALB AFRICAN AMERICAN MUSEUM BUILDING CONSTRUCT | 168300 | 168300 | 0% | Waiting on organization to select a site to proceed with land acquisition. | 6/30/2026 | 3/23/2023
Arts & Culture - NPO | 2022 | G2649 | African American Museum NPO | ALB AFRICAN AMERICAN MUSEUM FCLTY CONSTRUCT | 300000 | 122150.51 | 59.28% | Waiting on organization to select a site to proceed with land acquisition | 6/30/2026 | 3/3/2023
Arts & Culture - NPO | 2023 | H2786 | African American Museum NPO | AFRICAN AMERICAN MUS & CULTURAL CTR OF NM IMPR | 126490 | 126490 | Agreement not received from State | Waiting on organization to select a site to proceed with land acquisition | 6/30/2027
Arts & Culture - NPO | 2024 | I2700 | African American Museum NPO | AFRICAN AMERICAN MUS & CULTURAL CTR ACQ | 198000 | 198000 | 0% | Waiting on organization to select a site to proceed with land acquisition | 6/30/2028 | 9/6/2024
Office of Equity & Inclusion - NPO | 2024 | I2829 | AIO NPO | URBAN INDIGENOUS CTR REN | 225000 | 225000 | 0% | ​Survey results evaluation underway, estimated completion 12/6/24. Recommendations from results will determine scope and design of project. | 6/30/2028 | 9/6/2024
Parks & Recreation | 2023 | H2789 | Alameda Drain Trail | ALAMEDA PEDESTRIAN TRAIL CONSTRUCT | 3000000 | 3000000 | 0% | Waiting on MRGCD Agreement, NOO expected in late 2025 for construction on the trail. | 6/30/2027 | 11/13/2023
Parks & Recreation - NPO | 2021 | F2579 | Alameda Little League | ALB ALAMEDA LL CMPLX IMPROVE | 200000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 11/1/2021
Parks & Recreation - NPO | 2022 | G2650 | Alameda Little League | ALB ALAMEDA LL CONSTRUCT | 20000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2026 | 12/29/2022
Parks & Recreation - NPO | 2023 | H2788 | Alameda Little League | ALAMEDA LL FCLTY IMPROVE | 420750 | 138566 | 67.07% | NOO expected early 2025 for remaining balance. | 6/30/2027 | 11/15/2023
Parks & Recreation - NPO | 2024 | I2833 | Alameda Little League | VISTA ALAMEDA BASEBALL FCLTY IMPROVE | 510000 | 510000 | 0% | NOO expected in 2025 for league improvements 2025/2026 | 6/30/2028 | 8/21/2024
Parks & Recreation | 2023 | H2790 | Alamosa Park | ALAMOSA PK LIGHTING CONSTRUCT | 450000 | 431783.02 | 4.048% | NOO expected this November- December for phase 1 lighting | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2702 | Alamosa Park Playground | ALAMOSA PK PGRND IMPROVE | 420000 | 420000 | 0% | NOO expected in early 2025 for playground renovation | 6/30/2028 | 10/1/2024
Health, Housing, & Homelessness | 2024 | I2823 | Alamosa-Ted Gallegos HSSC Roof | ALB TED M. GALLEGOS CTR CONSTRUCT | 20000 | 20000 | 0% | Obtaining quotes to complete needed improvements. | 6/30/2028 | 9/6/2024
Municipal Development | 2024 | I4017 | ALBUQUERQUE DISTRICT SIX ART CORRIDORSAFETY IMPROVEMENT, EXTEND TIME, GENERAL FUND | ALBUQUERQUE DISTRICT SIX ART CORRIDORSAFETY IMPROVEMENT, EXTEND TIME, GENERAL FUND | 25000 | 25000 | 0% | ​Quote for equipment requested, due 12/15/24. Once received NOO will be submitted to NMDOT. | 6/30/2026 | Received
Municipal Development | 2024 | I4018 | ALBUQUERQUE DISTRICT SIX STREET LIGHTINGIMPROVEMENT, EXTEND TIME, GENERAL FUND | ALBUQUERQUE DISTRICT SIX STREET LIGHTINGIMPROVEMENT, EXTEND TIME, GENERAL FUND | 30000 | 0 | 100% | Waiting on NMDOT to approve NOO. | 6/30/2026 | 10/28/2024
Arts & Culture | 2021 | F2631 | Albuquerque Museum Education Center | ALB ABQ MUSEUM PHASE III CONSTRUCT | 190000 | 7700 | 95.95% | This project is short $2 million of the $9 million needed to begin this phase of construction. When fully funded, can break ground in 2025. | 6/30/2025 | 11/5/2021
Arts & Culture | 2022 | G2708 | Albuquerque Museum Education Center | ALB MUSEUM EDUCATION CTR CONSTRUCT | 772200 | 26191 | 96.61% | This project is short $2 million of the $9 million needed to begin this phase of construction. When fully funded, can break ground in 2025. | 6/30/2026 | 1/17/2023
Arts & Culture | 2023 | H2851 | Albuquerque Museum Education Center | MUSEUM ED CTR CONSTRUCT | 1440000 | 1440000 | Agreement not received from State | DFA believed this funding to be intended for a non-profit entity and placed it on a special conditions list. Three letters have been sent to clarify that it is a city-owned facility. The funding has not been released to CABQ. | 6/30/2027
Arts & Culture | 2024 | I2777 | Albuquerque Museum Education Center | ALB MUSEUM ED CTR CONSTRUCT | 1585000 | 1585000 | 0% | This project is short $2 million of the $9 million needed to begin this phase of construction. When fully funded, can break ground in 2025. | 6/30/2028 | 10/1/2024
Health, Housing, & Homelessness - NPO | 2022 | G2651 | All Faiths NPO | ALB ALL FAITHS VEH & EQUIP | 535000 | 535000 | Agreement not received from State | Waiting on Non-profit for Scope of Services for Use Agreement to meet anti-donation. | 6/30/2026
Parks & Recreation | 2022 | G2652 | Altura Park | ALB ALTURA PARK REN | 150000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2026 | 12/29/2022
Parks & Recreation | 2024 | I2704 | Altura Park | ALTURA PARK IMPROVE | 50000 | 50000 | 0% | NOO expected in early 2025 for resurfacing mid 2025 | 6/30/2028 | 8/23/2024
Albuquerque Police Department | 2023 | H2791 | APD Academy | APD ACAD IMPROVE | 342777 | 337119.24 | 1.651% | Waiting on quote from vendor. Project will be to upgrade Academy restrooms. Amount will be fully expended with this project. | 6/30/2027 | 11/3/2023
Albuquerque Police Department | 2024 | I2706 | APD Community Command Posts | ALB APD MOBILE COMMAND PRCHS | 125000 | 125000 | 0% | Waiting on quote from Ops Review to fully expend. | 6/30/2026 | 9/9/2024
Albuquerque Police Department | 2021 | F2643 | APD Equipment D3 | ALB POLICE DEPT PUBLIC SAFETY EQUIP | 20000 | 700 | 96.5% | ​The funds for the purchase of public safety equipment have been expended. Job Complete. Funds were used to purchase Speed Trailers. | 6/30/2025 | 10/13/2021
Albuquerque Police Department | 2022 | G2693 | APD Facilities | ALB LAW ENFORCE FACILITIES MODERNIZE REN | 178200 | 20925 | 88.26% | Waiting on quote from vendor. Project will be to upgrade Academy restrooms. Amount will be fully expended with this project. | 6/30/2026 | 1/9/2023
Albuquerque Police Department | 2022 | G2725 | APD Facilities | ALB PUB SFTY FCLTY & EQUIP IMPROVE | 100000 | 0.01 | 100% | Fully encumbered | 6/30/2026 | 1/10/2023
Albuquerque Police Department | 2023 | H2792 | APD Helicopter | APD HELICOPTER PRCHS | 617778 | 0 | 100% | Fully Encumbered PO - POL0025773 | 6/30/2025 | 11/13/2023
Albuquerque Police Department | 2024 | I2788 | APD Helicopter | ALB POLICE DEPT HELICOPTER PRCHS | 3045000 | 0 | 100% | Fully Encumbered PO - POL0025773 | 6/30/2026 | 9/9/2024
Albuquerque Police Department | 2024 | I2789 | APD Investigative Technology | POLICE DEPT INFO & INVESTIGATIVE TECH PRCHS | 175000 | 175000 | 0% | Waiting on Contract finalization. Once Contract is in place an NoO will be submitted for the Axon - Drone Project - 20K | 6/30/2026 | 9/9/2024
Albuquerque Police Department | 2024 | I2791 | APD Public Safety Field Technology | ALB POLICE DEPT SFTY FLD GRID TECH PRCHS | 510000 | 510000 | 0% | Waiting on Contract finalization. Once Contract is in place an NoO will be submitted for the Axon - Drone Project - $260K, $250K for Rail Trail/Sawmill Tech | 6/30/2026 | 9/9/2024
Albuquerque Police Department | 2023 | H2793 | APD Vehicles | APD VEHS PRCHS | 200000 | 6519 | 96.74% | ​Funds were used to purchase and equip police vehicles (F350 Trucks). Waiting on quotes to spend remaining funds ($6,519). | 6/30/2025 | 10/11/2023
Albuquerque Police Department | 2023 | H2859 | APD Vehicles | POLICE DEPT MOBILE COMMAND STN UNITS PRCHS | 180000 | 32241.25 | 82.09% | Awaiting vehicle delivery, remainder to be combined with other funding for additional vehicles. | 6/30/2025 | 10/11/2023
Albuquerque Police Department | 2024 | I2792 | APD Vehicles | POLICE VEH PRCHS | 50000 | 50000 | 0% | Waiting on quote from Ops Review to fully expend. | 6/30/2026 | 9/9/2024
Parks & Recreation | 2023 | H4040 | Artificial Turf | Artificial Turf Playing Fields Acquisition and Construction - Change to Improve Playing Fields | 160000 | 160000 | 0% | NOO expected in November 2024 for Ventana Pickleball courts due to scope change and expansion | 6/30/2025 | 12/8/2023
Youth & Family Services - NPO | 2021 | F2584 | Asian American Community Center NPO | ALB Asian American Cmty Ctr Construct | 15000 | 15000 | Agreement not received from State | 3rd phase of community outreach ongoing. Project lacks consensus and funding, Estimated budget is $35M (2025 legislative brief). Requires Use Agreement to meet Anti-Donation to receive Grant Agreement from LGD. | 6/30/2025
Youth & Family Services - NPO | 2022 | G2653 | Asian American Community Center NPO | ALB ASIAN CMTY CTR CONSTRUCT | 500696 | 500696 | 0% | Waiting on non-profit to determine use of funding. 3rd phase of community outreach ongoing. Estimated budget is $35M (2025 legislative brief). | 6/30/2026 | 12/29/2022
Youth & Family Services - NPO | 2023 | H4036 | Asian American Community Center NPO | Asian and Pacific Islander Community Center Construction - Extend Time | 457761.81 | 340246 | 25.67% | 3rd phase of community outreach ongoing. Project lacks consensus and funding. Estimated budget is $35M (2025 legislative brief). | 6/30/2025 | 9/18/2023
Youth & Family Services - NPO | 2023 | H2794 | Asian American Community Center NPO | ASIAN & PAC ISLD CMTY RESOURCE CTR CONSTRUCT | 200000 | 200000 | 0% | 3rd phase of community outreach ongoing. Project lacks consensus and funding. Estimated budget is $35M (2025 legislative brief). | 6/30/2027 | Received
Youth & Family Services - NPO | 2024 | I2707 | Asian American Community Center NPO | ASIAN/PACIFIC ISLANDER/NATIVE HAWAIIAN CTR CONSTRUCT | 150000 | 150000 | 0% | 3rd phase of community outreach ongoing. Project lacks consensus and funding. Estimated budget is $35M (2025 legislative brief). | 6/30/2028 | 9/6/2024
Municipal Development | 2022 | G3112 | Avenida Cesar Chavez | AVENIDA CESAR CHAVEZ & DOLORES HUERTA STREETS IMPR | 100000 | 100000 | 0% | ​Quote for design of Rail Trail in this area near Hispanic Cultural Center requested. Once received NOO to be submitted to NMDOT by 12/15/24 | 6/30/2026 | Received
Parks & Recreation | 2021 | F2585 | Balloon Fiesta Park | ALB BALLOON FIESTA PARK 50TH UPGRADES REN | 50000 | 0 | 100% | Funds fully expended. | 6/30/2025 | 8/12/2022
Parks & Recreation | 2021 | F2658 | Balloon Fiesta Park | ALB SPORTS MULTI-USE STADIUM CONSTRUCT | 4905202.05 | 0 | 100% | Project complete. Used for infrastructure upgrades. | 6/30/2025 | 6/29/2022
Parks & Recreation | 2022 | G2654 | BALLOON FIESTA PARK | ALB BALLOON FIESTA PARK IMPROVE | 40000 | 0 | 100% | Project Complete | 6/30/2026 | 8/29/2022
Parks & Recreation | 2022 | G2655 | BALLOON FIESTA PARK | ALB BALLOON FIESTA PARK REN | 150000 | 0 | 100% | Project complete. Used for site surveys and infrastructure improvements. | 6/30/2026 | 9/7/2022
Parks & Recreation | 2023 | H2782 | Balloon Fiesta Park | BALLOON FIESTA PARK LANDING SITES CONSTRUCT | 3000000 | 2721805.5 | 9.273% | Waiting on appraisal results. NOO and land purchase expected in late 2024. | 6/30/2027 | 10/26/2023
Parks & Recreation | 2023 | H2796 | Balloon Fiesta Park | BALLOON FIESTA PARK IMPROVE | 4315000 | 0 | 100% | Fully encumbered, project under construction. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2023 | H3260 | Balloon Fiesta Park | SPORTS & CULTURAL CTR CONSTRUCT | 4950000 | 4426516.34 | 10.58% | Waiting on PNM to complete design on electrical loop. | 6/30/2027 | 11/28/2023
Parks & Recreation | 2024 | I2710 | Balloon Fiesta Park | BALLOON FIESTA PK IMPROVE | 15575000 | 1378475.79 | 91.15% | Projects underway, remaining funding planned for additional projects currently in design. | 6/30/2028 | 8/3/2024
Parks & Recreation | 2024 | I4034 | Balloon Fiesta Park | ALBUQUERQUE SPORTS AND CULTURAL CENTER CONSTRUCTION--CHANGE TO BALLOON FIESTA PARK IMPROVEMENT--EXTEND TIME--SEVERANCE TAX BONDS.-- | 3556055 | 2083054.21 | 41.42% | Awaiting further funding for balloon fiesta infrastructure upgrades. Currently short 23M. We have raised over 35M to date. Encumbered funds used for permanent bathrooms. | 6/30/2026 | 8/3/2024
Arts & Culture | 2021 | F2580 | Balloon Museum | ALB And-Abruzzo Int Balloon Museum DVLP | 110000 | 85000 | 22.73% | Design is underway. Pending stakeholder meetings, this is fully-funded and construction is expected to begin in 2025. | 6/30/2025 | 9/22/2021
Arts & Culture | 2022 | G2656 | Balloon Museum | ALB BALLOON MUS EXHIBITS INSTALL | 230000 | 134999 | 41.3% | Design is underway. Pending stakeholder meetings, this is fully-funded and construction is expected to begin in 2025. | 6/30/2026 | 9/7/2022
Arts & Culture | 2023 | H3258 | Balloon Museum | INTNL BALLOON MUS ROOF & INFRA IMPROVE | 140000 | 140000 | 0% | Pending $2 million to fully fund Phase 1 of this project, construction can begin as soon as Fall 2025. | 6/30/2027 | 11/28/2023
Arts & Culture | 2024 | I2705 | Balloon Museum | ANDERSON-ABRUZZO INTRNATL BALLOON MUS IMPROVE | 700000 | 700000 | 0% | Pending $2 million to fully fund Phase 1 of this project, construction can begin as soon as Fall 2025. | 6/30/2028 | 9/6/2024
Arts & Culture | 2023 | H2826 | Balloon Museum Theater | INTRNATL BALLOON MUS VISITOR FCLTY IMPROVE | 603900 | 0 | 100% | This project is nearing completion and all funds have been encumbered or expended. | 6/30/2027 | 10/11/2023
Municipal Development | 2022 | G3113 | Barelas Great Blocks | BARELAS 4TH ST GREAT BLOCKS PROJECT IMPROVE | 390000 | 224344.19 | 42.48% | NOO pending approval from the state. Project took several years to accumulate the $6.9M required funding. Going out to bid by Jan 2025. Had July 2024 bid date scheduled, but pushed back due to legal challenges from a local business. | 6/30/2026 | Received
Municipal Development | 2023 | H4028 | Barelas Great Blocks | Fourth Street SW Improvements - Change to Acquire Rights of Way and to Improve Fourth Street SW and Sidewalks - Extend Time | 100000 | 100000 | Agreement not received from State | ​Waiting on Grant Agreement from NMDOT. Due to delays from NMDOT in producing grant agreement, we must reauthorize this grant again to utilize the funds prior to reversion. Project took several years to accumulate the $6.9M required funding. Going out to bid by Jan 2025. Had July 2024 bid date scheduled, but pushed back due to challenges from a local business. | 6/30/2025
Municipal Development | 2023 | G2074 | Barelas Great Blocks | Barelas Great Blocks | 1910000 | 1910000 | 0% | Project took several years to accumulate the $6.9M required funding. Had July 2024 bid date scheduled, but pushed back due to legal challenges from a local business. Going out to bid by Jan 2025. | 6/30/2026 | Received
Municipal Development | 2023 | H3287 | Barelas Great Blocks | 4TH ST GREAT BLOCKS ON MAIN ST IMPROVE | 300000 | 300000 | 0% | Project took several years to accumulate the $6.9M required funding. Going out to bid by Jan 2025. Had July 2024 bid date scheduled, but pushed back due to legal challenges from a local business. | 6/30/2027 | Received
Municipal Development | 2024 | H2121-2401 | Barelas Great Blocks | Barelas Great Blocks | 4000000 | 4000000 | 0% | Project took several years to accumulate the $6.9M required funding. Going out to bid by Jan 2025. Had July 2024 bid date scheduled, but pushed back due to legal challenges from a local business. | 6/30/2027 | 8/16/2024
Metropolitan Redevelopment | 2024 | I4035 | Barelas MRA | BARELAS LIVE/WORK INCUBATOR FOR CREATIVES--CHANGE TO BARELAS METROPOLITAN REDEVELOPMENT AREA IMPROVEMENT--EXTEND TIME--SEVERANCE TAX BONDS.-- | 148500 | 148500 | 0% | ​Funds will be used for traffic calming, and upgrades to trash receptables and parks in the Barelas area. MRA is coordinating with DMD, Solid Waste, and Parks on these improvements. | 6/30/2026 | 10/1/2024
Parks & Recreation | 2023 | H2800 | Barelas Park | BARELAS PK IMPROVE | 100000 | 100000 | 0% | NOO expected in 2025 for next phase design | 6/30/2027 | 10/11/2023
Parks & Recreation | 2022 | G2657 | Barelas Park | ALB BARELAS PARK REN | 200000 | 198 | 99.9% | Parking lot construction project completed October 2024. Awaiting final invoice. | 6/30/2026 | 8/29/2022
Parks & Recreation | 2024 | I2711 | Barelas Park - Phase 2 | ALB BARELAS PK PH 2 IMPROVE | 160000 | 160000 | 0% | NOO expected in 2025 for next phase renovation | 6/30/2028 | 8/23/2024
Senior Affairs | 2023 | H2004 | Barelas Senior Center Equip | BARELAS SENIOR CTR - MEALS EQUIP | 55000 | 55000 | 0% | 11/21/24 Waiting for fully executed agreement from State ALTSD, Obtained quote from National Restaurant Supply, will submit NOO to state for purchase approval. | 6/30/2027 | Received
Senior Affairs | 2024 |  | Barelas Senior Center Reno | ALB BARELAS SENIOR CTR REPAIR | 1500000 | 1500000 | Agreement not received from State | 10/25/24 Waiting on State for award letter from ALTSD
Senior Affairs | 2024 | I2009 | Barelas Senior Center Reno | ALB BARELAS SENIOR CTR REPAIR & IMPROVE | 100000 | 100000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Parks & Recreation | 2024 | I2643 | Barstow/Desert Ridge Trails/Rancho de Palomas Parks | ALB PK SHADE STRUCT UPGRADE | 100000 | 100000 | 0% | NOO expected in mid 2025 for shade installations 2025 | 6/30/2028 | 8/3/2024
Senior Affairs | 2021 | F2007 | Bear Canyon Senior Center | ALB BEAR CANYON SENIOR CTR REN | 105000 | 0 | 100% | 11/21/24 CLOSE OUT PROJECT. This grant is fully executed and project complete. | 6/30/2025 | Received
Senior Affairs | 2021 | F2008 | Bear Canyon Senior Center | ALB BEAR CANYON SENIOR CTR VEH | 29670 | 0 | 100% | 11/21/24 CLOSE OUT PROJECT. This grant is fully executed and project complete. | 6/30/2025 | Received
Parks & Recreation | 2024 | I2712 | Betsy Patterson Pool | ALB BETSY PATTERSON POOL CONSTRUCT | 50000 | 0 | 100% | NOO received 10/21/2024 for 2025 pool tile construction | 6/30/2028 | 8/23/2024
Arts & Culture | 2023 | H2801 | BioPark | BIOPARK AQUARIUM IMPROVE | 594275 | 559681.44 | 5.821% | Phase I of this project is complete (demolition). Phase II is now underway with SMPC architects on contract for design. | 6/30/2027 | 10/31/2023
Arts & Culture | 2024 | I2696 | BioPark Aquarium Improvements | ABQ BIOPARK AQUARIUM IMPROVE | 350000 | 350000 | 0% | This funding is intended for construction on Phase II once design is complete. | 6/30/2028 | 9/6/2024
Parks & Recreation | 2024 | I2804 | Bosque Renovation Improvements | RIO GRANDE STATE PK IMPROVE | 1635000 | 1635000 | 0% | NOO expected in late 2025 for 2026 implementation | 6/30/2028 | 8/3/2024
Parks & Recreation | 2024 | I2714 | Brentwood Hills Park | ALB BRENTWOOD HILLS PK IMPROVE | 150000 | 150000 | 0% | NOO expected in early 2025 for resurfacing mid 2025 | 6/30/2028 | 8/23/2024
Municipal Development | 2022 | G3114 | Broadway Blvd. | BROADWAY BLVD CONSTRUCT | 325000 | 24434 | 92.48% | ​NOO issued and design underway | 6/30/2026 | Received
Municipal Development | 2023 | H3296 | Broadway Blvd. | BROADWAY BLVD IMPROVE | 50000 | 0 | 100% | NOO received from NMDOT 11/14/2024. NTP Issued to contractor. | 6/30/2027 | Received
Municipal Development | 2024 | I3252 | Broadway Boulevard Construct | Broadway Boulevard Construct | 250000 | 250000 | 0% | ​Agreement received 10/28/24. Pending results of traffic calming study undertaken with previous capital outlay. Once received, a scope and fee will be requested for design | 6/30/2028 | 10/28/2024
ABQ Ride/Transit | 2022 | G2659 | Bus Stops | ALB BUS STOPS IMPROVE | 50000 | 29735 | 40.53% | ​NoOs submitted to date $20,265.72. The next step in the project is to do some concrete work at some of the bus stops. | 6/30/2026 | 12/29/2022
Health, Housing, & Homelessness - NPO | 2022 | G2660 | Calle Cuarta - Yes Housing NPO | ALB CALLE CUARTA AFFORDABLE HOUSING DVLP IMPROVE | 130000 | 0 | 100% | Fully encumbered. | 6/30/2026 | 3/27/2024
Health, Housing, & Homelessness - NPO | 2023 | H2785 | Calle Cuarta - Yes Housing NPO | AFFORDABLE HSG CONSTRUCT | 250000 | 0 | 100% | Fully encumbered. | 6/30/2027 | 11/11/2024
Parks & Recreation | 2021 | F2587 | Candelaria Nature Preserve | ALB CANDELARIA NATURE PRESERVE REN | 550000 | 181117.96 | 67.07% | Bids for bridge construction and Tree Nursery Tract due December 2024. NOO expected when bids are received. | 6/30/2025 | 9/9/2021
Parks & Recreation | 2022 | G2661 | Candelaria Nature Preserve | ALB CANDELARIA NATURE PRESERVE IMPROVE | 250000 | 250000 | 0% | NOO expected this December 2024 for phase 1 construction. | 6/30/2026 | 9/2/2022
Parks & Recreation | 2023 | H2802 | Candelaria Nature Preserve | CANDELARIA NATURE PRESERVE IMPROVE | 310000 | 310000 | 0% | NOO expected this December 2024 for phase 1 construction. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2716 | Candelaria Nature Preserve | CANDELARIA NATURE PRESERVE IMPROVE | 300000 | 300000 | 0% | NOO expected this December 2024 for phase 1 construction. | 6/30/2028 | 8/23/2024
Parks & Recreation | 2022 | G2662 | Carnuel Village Open Space | ALB CARNUEL VILLAGE ARCHAELOGICAL SITE IMPROVE | 100000 | 100000 | 0% | NOO expected in early 2025 for archaeological work | 6/30/2026 | 12/29/2022
Parks & Recreation - NPO | 2021 | F2588 | Casa Barelas Greenhouse | ALB CASA BARELAS CMTY GREENHOUSE & GARDEN CONSTR | 50000 | 50000 | 0% | Waiting on Non-profit for project scope. | 6/30/2025 | 11/18/2021
Parks & Recreation | 2021 | F2589 | Casa Grande Linear Park | ALB CASA GRANDE LINEAR PK IMPROVE | 25000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 9/9/2021
Senior Affairs | 2021 | F2010 | Casa Kitchen | ALB CASA SENIOR NUTRITION & TRANSPORT VEH | 266950 | 14932 | 94.41% | 11/21/24 CLOSE OUT PROJECT. This grant is fully executed and project complete. | 6/30/2025 | Received
Senior Affairs | 2023 | H2005 | Casa Kitchen | CASA KITCHEN - MEALS EQUIP | 300000 | 300000 | 0% | 11/21/24 Waiting for fully executed agreement from ALTSD, Obtained quote from National Restaurant Supply, will submit NOO to state for purchase approval. | 6/30/2027 | Received
Arts & Culture | 2023 | H3155 | Casa San Ysidro | CASA SAN YSIDRO IMPROVE | 150000 | 150000 | 0% | Agreement received 11/15/24 and department will move forward on upgrades as soon as monies are received. | 6/30/2027 | 11/25/2024
Municipal Development | 2021 | F2975 | CD3 Lighting | ALB CITY COUNCIL DIST 3 STREETLIGHTS INSTALL | 50000 | 0 | 100% | Pending NMDOT approval of NOO. | 6/30/2025 | 9/16/2021
Municipal Development | 2022 | G3109 | CD3 Lighting | ALB NEIGHBORHOOD INTERSECTION LIGHTING CONSTRUCT | 65000 | 0 | 100% | Pending NOO approval from NMDOT | 6/30/2026 | Received
ABQ Ride/Transit | 2023 | H2803 | Central & Tramway Pedestrian Safety | CENTRAL & TRAMWAY PUB SFTY FENCE INSTALL | 94000 | 0 | 100% | Fully encumbered, fencing installation underway. | 6/30/2027 | 10/11/2023
Arts & Culture | 2023 | H2804 | Central & Unser Library | CENTRAL & UNSER LIBRARY IMPROVE | 198000 | 108000 | 45.45% | Project is underway and completion is expected by the end of January 2025. | 6/30/2027 | 10/3/2023
Youth & Family Services | 2024 | I2717 | Cesar Chavez CC | ALB CESAR CHAVEZ CMT CTR FITNESS EQUIP PRCHS | 100000 | 100000 | 0% | NoO will be submitted 11/24 | 6/30/2026 | 9/9/2024
Parks & Recreation | 2024 | I2718 | Chapparal Elementary Splashpad | CHAPPARAL SPLASH PAD & PK CONSTRUCT | 500000 | 500000 | 0% | Waiting on APS on use of land | 6/30/2028 | 8/23/2024
Arts & Culture - NPO | 2024 | I2719 | Cheese Aging Equipment Purchase NPO | CHEESE AGING EQUIP PRCHS | 200000 | 200000 | 0% | Waiting on the organization to submit the final equipment list. | 6/30/2026 | 9/6/2024
Arts & Culture | 2024 | I2713 | Children's Fantasy Gardens Renovations & Upgrades | ALB BIOPARK CHILDRENS FANTASY GARDEN REN | 555000 | 555000 | 0% | The City has identified an architect, and we expect design to begin in Spring 2025, and construction to begin in Summer 2026. | 6/30/2028 | 9/6/2024
Senior Affairs | 2021 | F2590 | Cibola Loop Multigen | ALB CIBOLA LOOP COMMUNITY CENTER CONSTRUCT | 495000 | 0 | 100% | 11/21/24 We need a minimum of $2 Million dollars this session to complete project on time. | 6/30/2025 | 9/9/2021
Senior Affairs | 2022 | G2663 | Cibola Loop Multigen | ALB CIBOLA LOOP MULTIGENERATIONAL CMPLX CONSTRUCT | 100000 | 0 | 100% | 11/21/24 We need a minimum of $2 Million dollars this session to complete project on time. | 6/30/2026 | 8/29/2022
Senior Affairs | 2023 | H2805 | Cibola Loop Multigen | CIBOLA LOOP MULTI-GEN CENTER PH 1 CONSTRUCT | 891000 | 0 | 100% | 11/21/24 We need a minimum of $2 Million dollars this session to complete project on time. | 6/30/2027 | 10/11/2023
Senior Affairs | 2024 | I2720 | Cibola Loop Multigen | CIBOLA LOOP MULTIGENERATIONAL CTR CONSTRUCT | 1188000 | 0 | 100% | 11/21/24 We need a minimum of $2 Million dollars this session to complete project on time. | 6/30/2028 | 7/26/2024
Parks & Recreation | 2022 | G2664 | Clayton Heights Park | ALB CLAYTON HEIGHTS PARK CONSTRUCT | 110000 | 110000 | 0% | NOO expected early 2025 for phase 1 construction. | 6/30/2026 | 4/11/2023
Parks & Recreation | 2023 | H2806 | Clayton Heights Park | CLAYTON HEIGHTS NBRHD PK CONSTRUCT | 100000 | 100000 | 0% | NOO expected early 2025 for phase 1 construction. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2721 | Community Garden and Agricultural Improvement Projects | CMTY GARDEN CONSTRUCT | 50000 | 50000 | 0% | NOO expected in 2025 for design for a garden implementation in 2026 | 6/30/2028 | 8/23/2024
Municipal Development | 2024 | I3254 | Constitution Ave and Washington Construct (McDuffie) | CONSTITUTION AVE & WASHINGTON ST CONSTRUCT | 450000 | 450000 | 0% | ​Agreement received 10/28/24. McDuffie Traffic improvements in design. Capital outlay to be used for construction once design and engineers estimates are complete | 6/30/2028 | 10/28/2024
Municipal Development | 2022 | G3116 | Coors Pedestrian | COORS BLVD SAFETY & PEDESTRIAN INFRA IMPROVE | 75000 | 75000 | 0% | ​Pending scope and fee from consultant for design, due 12/31/24. Once received NOO to be requested from NMDOT | 6/30/2026 | Received
Municipal Development | 2023 | H3297 | Coors Pedestrian | COORS BLVD SIDEWALKS IMPROVE | 100000 | 55000 | 45% | NOO issued by NMDOT 11/14/2024. NTP issued to contractor. | 6/30/2027 | Received
Albuquerque Fire Rescue | 2023 | H2807 | Coronado Park - Fire Station 4 | CORONADO PK FIRE RESCUE TRAIN & RESPONSE FCLTY | 5225000 | 4197212 | 19.67% | ​Currently in design. Coronado Park - Fire Station 4. Waiting on construction estimates based on design. | 6/30/2027 | 10/11/2023
Albuquerque Fire Rescue | 2024 | I2739 | Coronado Park Fire Rescue Training and Response Center | ALB FIRE RESCUE CORONADO PK FIRE STN 4 CONSTRUCT | 100000 | 100000 | 0% | ​Currently in design. Coronado Park - Fire Station 4. Waiting on construction estimates based on design. | 6/30/2028 | 9/12/2024
Parks & Recreation | 2024 | I2724 | Creighton Park | ALB CREIGHTON PARK CONSTRUCT | 570000 | 503003.44 | 11.75% | NOO expected in early December 2025 for design | 6/30/2028 | 8/20/2024
Parks & Recreation | 2022 | G2666 | Crestview Bluff Open Space | ALB CRESTVIEW BLUFF IMPROVE | 40000 | 0 | 100% | ​NOO expected this 2025 for design. | 6/30/2026 | 12/29/2022
Parks & Recreation | 2022 | G4014 | Crestview Bluffs Open Space | REAUTHORIZATION Crestview Bluffs Open Space Area | 95000 | 0 | 100% | ​NOO expected this 2025 for design. | 6/30/2025 | 9/21/2022
Parks & Recreation | 2024 | I4016 | Crestview Bluff Open Space | Crestview Bluff | 112059 | 112059 | 0% | NOO expected in early 2025 for design | 6/30/2026 | 8/23/2024
Health, Housing, & Homelessness - NPO | 2023 | H4044 | Cuidando los Ninos NPO | Child Care Program Playground Equipment Purchase - Change to Equip and Improve a Facility for Unhoused Families - Extend Time | 15000 | 15000 | 0% | ​ Funding is currently short to complete project due to missing grant agreement from DFA for grant transferred from Bernalillo County. Project quote for architectural design and engineering is estimated at $540K. Funding will support fees for Dyron Murphy to design additions to the early childhood campus located on site. | 6/30/2027 | 12/28/2023
Health, Housing, & Homelessness - NPO | 2023 | H4043 | Cuidando los Ninos NPO | Children and Families Facility Improvements - Change to Improve Albuquerque Facility for Unhoused Families in Albuquerque | 65000 | 65000 | 0% | ​ Funding is currently short to complete project due to missing grant agreement from DFA for grant transferred from Bernalillo County. Project quote for architectural design and engineering is estimated at $540K. Funding will support fees for Dyron Murphy to design additions to the early childhood campus located on site. | 6/30/2027 | 12/3/2023
Health, Housing, & Homelessness - NPO | 2023 | H4042 | Cuidando los Ninos NPO | Bernalillo County Homeless Family Facility Construction - Change to Improve a Facility for Unhoused Families in Albuquerque | 464204 | 464204 | Agreement not received from State | Waiting on State for Grant Agreement, this grant was transferred from Bernalillo County - ​Until the state agreement is approved the project lacks funds to move forward. | 6/30/2027
Health, Housing, & Homelessness - NPO | 2023 | H2818 | Cuidando los Ninos NPO | FAMILIES W/O HOMES PRESCHOOL CONSTRUCT | 1356490 | 1356490 | 0% | ​ Funding is currently short to complete project due to missing grant agreement from DFA for grant transferred from Bernalillo County. Project quote for architectural design and engineering is estimated at $540K. Funding will support fees for Dyron Murphy to design additions to the early childhood campus located on site. | 6/30/2027 | 11/9/2024
Health, Housing, & Homelessness - NPO | 2023 | H4045 | Cuidando los Ninos NPO | Homeless Children Facility Vehicle Purchase and Improvements - Change to Improve a Facility for Unhoused Families - Extend Time | 143550 | 143550 | 0% | ​ Funding is currently short to complete project due to missing grant agreement from DFA for grant transferred from Bernalillo County. Project quote for architectural design and engineering is estimated at $540K. Funding will support fees for Dyron Murphy to design additions to the early childhood campus located on site. | 6/30/2025 | 9/15/2023
Health, Housing, & Homelessness - NPO | 2024 | I2754 | Cuidando los Ninos NPO | JOHN MARSHALL HSSC CLASSROOMS REN | 178200 | 178200 | 0% | Project quote is 540,00, Project Funding is short $361,800. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2023 | H2808 | Cutler Park | CUTLER PARK IMPROVE | 325000 | 0 | 100% | NOO expected in December 2025 for a drinking fountain and tables | 6/30/2027 | 10/11/2023
Arts & Culture | 2021 | F2653 | DAC Warehouse | ALB SHARED WAREHOUSE FOR MUSEUMS CONSTRUCT | 10000 | 10000 | 0% | Site plans and estimates are complete. Phase 1 construction to being in early 2025. | 6/30/2025 | 10/28/2021
Municipal Development | 2024 | M700125 | Dalkia Downtown | Safer & Smarter Downtown Albuquerque Project | 700000 | 0 | 100% | ​Fully Encumbered, using for downtown lighting circuits. | 12/30/2024 | Received
Municipal Development | 2023 | H3221-2 | Dalkia Downtown | Safer & Smarter Downtown Albuquerque Project | 1100000 | 30878.61 | 97.19% | Project complete, remainder to be combined with local funds for additional circuits. | 6/30/2027 | Received
Parks & Recreation | 2021 | F2594 | Daniel Webster Park | ALB DANIEL WEBSTER PARK REN | 350000 | 0 | 100% | NOO expected early 2025 for lighting | 6/30/2025 | 9/9/2021
Parks & Recreation | 2024 | I2781 | Daniel Webster Park | ALB OFFICER DANIEL WEBSTER PARK CONSTRUCT | 260000 | 260000 | 0% | NOO expected in 2025 for park improvements | 6/30/2028 | 8/3/2024
Health, Housing, & Homelessness | 2023 | H2809 | Desert Hills | DESERT HILLS ACQ | 70000 | 70000 | 0% | In order complete this project it would require an additional $14.4M | 6/30/2027 | 10/11/2023
Albuquerque Police Department | 2023 | H2811 | Domestic Violence Resource Center NPO | DOMESTIC VIOLENCE COUNSELING OFC ACQ | 441490 | 441490 | 0% | ​NPO non-responsive for funding, will Reauth for use at the Family Advocacy Center | 6/30/2025 | Received
Parks & Recreation | 2024 | I2727 | Dulcinea Park | DULCINEA PK IMPROVE | 150000 | 150000 | 0% | NOO expected for early 2025 for playground purchase | 6/30/2028 | 8/20/2024
Municipal Development | 2024 | I3253 | East Central Ped Lighting | CENTRAL AVE UPGRADE | 75000 | 75000 | 0% | ​Agreement Received 10/27/24 - Pending quote for purchase of decorative lighting, due 12/15/24. To be used towards the East Central Lighting project between Eubank and Louisiana. Once quote received NOO to be requested from NMDOT | 6/30/2028 | 10/27/2024
Municipal Development | 2023 | H3298 | East Central Ped Lighting | EAST CENTRAL AVE ST LIGHT IMPROVE | 200000 | 200000 | 0% | Pending quote for purchase of decorative lighting, due 12/15/24. To be used towards the East Central Lighting project between Eubank and Louisiana. Once quote received NOO to be requested from NMDOT | 6/30/2027 | Received
Municipal Development | 2024 | I3255 | East Central Ped Lighting | E CENTRAL AVE LIGHT CONSTRUCT | 250000 | 250000 | 0% | ​Agreement received 10/28/24. Scope and fee to be requested for design of lighting project between Eubank and Tramway, due 12/31/24 | 6/30/2028 | 10/28/2024
Municipal Development | 2022 | G2737 | East Central Ped Lighting | ALB SE ALBUQUERQUE STREET LIGHT UPGRADE | 50000 | 50000 | 0% | Quote for lights anticipated 12/15/24, NOO to DFA to follow. Will be used to purchase lights as part of East Central Pedestrian Lighting project Eubank to Louisiana | 6/30/2026 | 9/2/2022
Parks & Recreation | 2024 | I2729 | East San Jose Pool | ALB EAST SAN JOSE POOL REN | 25000 | 10061.65 | 59.75% | NoO received for deck repairs. Scheduling with contractor for construction. | 6/30/2028 | 8/20/2024
Parks & Recreation - NPO | 2021 | F2596 | Eastdale Little League | ALB EASTDALE LL BATTING CAGES CONSTRUCT | 10000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 11/1/2021
Parks & Recreation - NPO | 2021 | F2597 | Eastdale Little League | ALB EASTDALE LL RESTROOM ADA COMPLIANCE CONSTRUCT | 154000 | 0 | 100% | Project under construction. Completion expected 2025. | 6/30/2025 | 9/9/2021
Parks & Recreation - NPO | 2022 | G2669 | Eastdale Little League | ALB EASTDALE LL BATHRM CONSTRUCT | 257400 | 0 | 100% | Project under construction. completion expected 2025. | 6/30/2026 | 11/28/2022
Parks & Recreation - NPO | 2022 | G2670 | Eastdale Little League | ALB EASTDALE LL LIGHTING PLAN | 20000 | 20000 | 0% | NOO expected 2025 for lighting. | 6/30/2026 | 12/2/2022
Parks & Recreation - NPO | 2023 | H2797 | Eastdale Little League | BALLOON FIESTA PK EASTDALE LL FIELDS REPAIR | 80000 | 80000 | 0% | NOO expected in December 2024 - January 2025 for next phase field work | 6/30/2027 | 10/11/2023
Parks & Recreation - NPO | 2023 | H2798 | Eastdale Little League | BALLOON FIESTA PK EASTDALE LL SCOREBOARDS CONS | 70000 | 70000 | 0% | NOO expected in December 2024 - January 2025 for scoreboards | 6/30/2027 | 10/11/2023
Parks & Recreation - NPO | 2023 | H2799 | Eastdale Little League | BALLOON FIESTA PK EASTDALE LL TURF IMPROVE | 30000 | 30000 | 0% | NOO expected in December 2024 - January 2025 for next phase field improvements. | 6/30/2027 | 10/11/2023
Parks & Recreation - NPO | 2024 | I2708 | Eastdale Little League | BALLOON FIESTA PK BB FLD CAGES CONSTRUCT | 50000 | 50000 | 0% | NOO expected for 2025 for use prior to the next season | 6/30/2028 | 8/23/2024
Parks & Recreation - NPO | 2024 | I2709 | Eastdale Little League | BALLOON FIESTA PK BB FLD IMPROVE | 100000 | 100000 | 0% | NOO expected for 2025 for use prior to the next season | 6/30/2028 | 8/23/2024
Parks & Recreation - NPO | 2024 | I2846 | Eastdale Little League | BALLOON FIESTA PK FCLTY IMPROVE | 25000 | 25000 | 0% | NOO expected for 2025 for use prior to the next season | 6/30/2028 | 8/23/2024
Parks & Recreation | 2022 | G2671 | Eisenhower Pool | ALB EISENHOWER SWIMMING POOL REPAIR | 145000 | 0 | 100% | Project complete. Used for pool gutter remodel. | 6/30/2026 | 12/29/2022
Parks & Recreation | 2023 | H2812 | Eisenhower Pool | EISENHOWER POOL FCLTY IMPROVE | 113850 | 8812.03 | 92.26% | Remaining funding will be used for restroom upgrades. Waiting on estimate from vendor. NoO expected 1/15/2025. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2730 | Eisenhower Pool | EISENHOWER POOL RPLC | 100000 | 100000 | 0% | Estimates requested from vendor. NoO expected in January 2025. Funds will be used for bathroom upgrades. | 6/30/2028 | 8/20/2024
Parks & Recreation | 2021 | F2599 | El Oso Grande Park | ALB EL OSO GRANDE PK LIGHT INSTALL | 50000 | 2087.92 | 95.82% | Remaining balance to be used for equipment. | 6/30/2025 | 9/9/2021
Parks & Recreation | 2023 | H2813 | El Oso Grande Park | EL OSO GRANDE PK IMPROVE | 30000 | 30000 | 0% | NOO expected in December 2024 for a drinking fountain and seating. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2731 | El Oso Grande Park | EL OSO GRANDE PK IMPROVE | 40000 | 40000 | 0% | NOO expected in December 2024 for drinking fountain and seating. | 6/30/2028 | 8/20/2024
Parks & Recreation | 2021 | F2600 | Elena Gallegos Open Space | ALB ELENA GALLEGOS OPEN SPACE EDUCATION CENTER CONSTRUCT | 30000 | 66.77 | 99.78% | NOO expected in 2025 for design of improvements. | 6/30/2025 | 9/9/2021
Parks & Recreation | 2024 | I2732 | Elena Gallegos Open Space | ALB ELENA GALLEGOS OPEN SPACE IMPROVE | 200000 | 200000 | 0% | NOO expected for 2025 for design in new ADA improvements and the balance for 2026 for phase 1 | 6/30/2028 | 8/20/2024
Parks & Recreation | 2024 | I2733 | Embudo Hills Park Playground | EMBUDO HILLS PK PGRND IMPROVE | 150000 | 150000 | 0% | NOO expected in 2025 for design and 2026 for improvements | 6/30/2028 | 8/20/2024
Health, Housing, & Homelessness - NPO | 2022 | G2673 | Enlace Communitario NPO | ALB ENLACE COMUNITARIO FCLTY REN | 25000 | 25000 | Agreement not received from State | Awaiting Scope of Services from Non-profit to form Use Agreement to meet anti-donation, so grant agreement can be released. | 6/30/2026
Health, Housing, & Homelessness - NPO | 2024 | I2735 | Equitable Homeownership Project to Address Racial Wealth Gap | EQUITABLE HSING CONSTRUCT | 275000 | 275000 | 0% | Waiting on Grant Agreement from DFA - CIP to clear Special Conditions. | 6/30/2028 | Received
Arts & Culture | 2023 | H2815 | Erna Fergusson Library | ERNA FERGUSSON LIBRARY REN | 148500 | 148500 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2027 | 10/11/2023
Arts & Culture | 2024 | I2736 | Erna Fergusson Library | ALB ERNA FERGUSSON LIB REN | 35000 | 35000 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2028 | 9/06/2024
Arts & Culture | 2023 | H2816 | Ernie Pyle Library | ERNIE PYLE PUBLIC LIBRARY REN | 100000 | 100000 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2027 | 10/11/2023
Arts & Culture | 2024 | I2737 | Ernie Pyle Library | ERNIE PYLE LIB REN | 272250 | 272250 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2028 | 9/6/2024
Arts & Culture - NPO | 2021 | F2603 | Explora | ALB EXPLORA SCIENCE & CHILDRENS MUSEUM EXPAND | 1160000 | 0 | 100% | ​Project is complete. Ribbon cutting 1/5/23 with numerous State Reps and Legislators in attendance. | 6/30/2025 | 9/22/2021
Arts & Culture - NPO | 2022 | G2674 | Explora | ALB EXPLORA MUSEUM CAMPUS EXPAND | 1361250 | 379101 | 72.15% | ​Design Development for Explora Brilliante is complete. Construction is expected to begin at the end of the year, 2024. | 6/30/2026 | 12/29/2022
Arts & Culture - NPO | 2023 | H2817 | Explora | SCI CTR & CHILDREN'S MUS CONSTRUCT | 2200883 | 200883 | 90.87% | Construction begins on this project in November 2024. | 6/30/2027 | 4/4/2024
Arts & Culture | 2024 | I2812 | Explora Brillante Early Childhood Center | SCI CTR & CHILDREN'S MUS CONSTRUCT | 6113349 | 6113349 | 0% | Construction begins on this project in November 2024 | 6/30/2028 | 9/6/2024
Health, Housing, & Homelessness | 2023 | H2824 | FCS HSSC | HEALTH & SOCIAL SERVICE CTRS IMPROVE | 50000 | 0 | 100% | Fully encumbered, using for Alamosa HSSC HVAC Controls. | 6/30/2027 | 10/11/2023
Albuquerque Fire Rescue | 2021 | F2607 | Fire Academy | ALB FIRE RESCUE TRAINING FCLTY REN | 625000 | 0 | 100% | ​Project complete. Funding was for a Training Structure for Albuquerque Fire. | 6/30/2025 | 9/9/2021
Albuquerque Fire Rescue | 2022 | G2676 | Fire Station 11 | ALB FIRE RESCUE STN 11 REN | 50000 | 0 | 100% | ​Project complete. Used for Fire Station 11 renovations. | 6/30/2026 | 12/29/2022
Albuquerque Fire Rescue | 2021 | F2606 | Fire Station 12 | ALB FIRE RESCUE STN 12 IMPROVE | 117500 | 0 | 100% | ​Project complete. Design services for fire station 12. | 6/30/2025 | 9/9/2021
Albuquerque Fire Rescue | 2024 | I2740 | Fire Station 12 | ALB FIRE STN 12 CONSTRUCT | 1225000 | 0 | 100% | ​Fully Encumbered, project under construction. | 6/30/2028 | 9/12/2024
Albuquerque Fire Rescue | 2023 | H2821 | Fire Station 14 | FIRE STN 14 IMPROVE | 148500 | 59198.37 | 60.14% | ​Funding used for roof repairs for Fire Station 14. | 6/30/2025 | 10/11/2023
Arts & Culture - NPO | 2022 | G2678 | Flamenco Works NPO | ALB FLAMENCO WORKS DANCE SCHL FURNISH | 285000 | 285000 | Agreement not received from State | ​Waiting on grant agreement from Local Government Division. | 6/30/2026
Parks & Recreation | 2021 | F2611 | Foothills Open Space | ALB FOOTHILLS TRAILHEAD LIGHT INSTALL | 15000 | 15000 | 0% | NOO expected this Dec 2024 for installation in early 2025 for a solar light | 6/30/2025 | 9/9/2021
Parks & Recreation | 2022 | G2679 | Foothills Open Space | ALB FOOTHILLS OPEN SPACE ED CTR IMPROVE | 50000 | 50000 | 0% | NOO expected in 2025 for design to expand uses in the park for lighting | 6/30/2026 | 9/7/2022
Parks & Recreation | 2022 | G2680 | Foothills Open Space | ALB FOOTHILLS OPEN SPACE IMPROVE | 150000 | 59026.48 | 60.65% | NOO expected in 2025. | 6/30/2026 | 9/7/2022
Albuquerque Police Department | 2021 | F2610 | Foothills Police Station | ALB FOOTHILLS AREA COMMAND POLICE STN REN | 227700 | 3237 | 98.58% | NOO to be submitted to State for remaining funds by Jan 2025. Funds used to improve Foothills Area Command. | 6/30/2025 | 9/9/2021
Parks & Recreation | 2024 | I3248 | Four Hills Village Bicycle Loop Construct | ALB FOUR HILLS VILLAGE BICYCLE LOOP CONSTRUCT | 50000 | 50000 | 0% | NOO expected this December 2024 | 6/30/2028 | 11/11/2024
Health, Housing, & Homelessness - NPO | 2022 | G2717 | GAHP NPO | ALB PAH! HILAND DEAF BLIND & HARD OF HEARING COMPL | 400000 | 4000 | 99% | ​As of 10/8/2024, funding has been expended on PAH! Hiland Plaza. This project has been completed. | 6/30/2025 | 2/21/2023
Health, Housing, & Homelessness | 2021 | F2612 | Gateway Center | ALB MULTI SITE GATEWAY CTR CONSTRUCT | 3941145 | 0 | 100% | ​This funding fully encumbered, part of larger project at Gateway Center. | 6/30/2025 | 9/22/2021
Health, Housing, & Homelessness - NPO | 2021 | F2604 | Gateway Center | ALB FAMILY SERVICES SFTY & EQUIP UPGRADE | 40000 | 40000 | Agreement not received from State | Unknown non-profit requested funding, exhausted attempts to locate organization, so did not utilize funds. Using at Gateway prior to reversion. | 6/30/2025
Health, Housing, & Homelessness | 2022 | G2742 | Gateway Center | ALB SUPPORTIVE HOUSING REHAB ACQ | 225000 | 0 | 100% | Funds have been allocated. Predevelopment underway. | 6/30/2026 | 2/27/2023
Health, Housing, & Homelessness | 2022 | G2681 | Gateway Center | ALB GIBSON HEALTH HUB IMPROVE | 417539 | 417539 | 0% | Agreement received 11/19/24 - Proposals due 11/22/24, NOO encumbrance by 11/27/24 | 6/30/2026 | 11/19/2024
Health, Housing, & Homelessness | 2023 | H2822 | Gateway Center | GATEWAY CTR MEDICAL TRTMNT & CARE FCLTY CONSTR | 9926490 | 0 | 100% | ​Fully encumbered, project under construction, approximately 50% complete. | 6/30/2027 | 10/11/2023
Health, Housing, & Homelessness - NPO | 2023 | H4030 | Gateway Center | Day Shelter and Behavioral Health Services Center Purchase and Construction - Change to Construct a Day Shelter and Health Center in the Gibson Health Hub - Extend Time | 371250 | 145183 | 60.89% | Will be fully encumbered by 12/1/24 | 6/30/2025 | 9/18/2023
Health, Housing, & Homelessness | 2024 | I2746 | Gateway Center | GIBSON HEALTH HUB TRAUMA CTR CONSTRUCT | 143550 | 0 | 100% | ​This funding fully encumbered, part of larger project at Gateway Center. | 6/30/2028 | 10/1/2024
Health, Housing, & Homelessness | 2024 | I2745 | Gateway Center | GIBSON HEALTH HUB EXPAND | 465300 | 465300 | 0% | ​​To be used for first floor Housing Navigation Center expansion East Suite at Gateway Center. Proposals due 11/22/24, NOO encumbrance by 11/27/24 | 6/30/2028 | 8/3/2024
Health, Housing, & Homelessness | 2024 | I4013 | Gateway Center | AFFORDABLE HOUSING CONSTRUCT | 2408153 | 2408153 | 0% | Proposals due 11/22/24, NOO encumbrance by 11/27/24 | 6/30/2026 | 8/3/2024
Health, Housing, & Homelessness | 2024 | I2839 | Gateway West | WEST SIDE EMERGENCY HOUSING SPACE IMPROVE | 100000 | 100000 | 0% | Project underway under different grant funding, utilizing this for additional work once previous work completed. | 6/30/2028 | 9/6/2024
Health, Housing, & Homelessness | 2021 | F2670 | Gateway Youth - San Mateo Inn | ALB YOUTH TEMPORARY HOUSING FCLTY | 455000 | 0 | 100% | ​Previous NPO grant, accumulating funds for large building purchase, could not obtain sufficient funding in time, so used at San Mateo Inn City Youth Shelter. | 6/30/2025 | 7/22/2022
Health, Housing, & Homelessness - NPO | 2021 | F2669 | Gateway Youth - San Mateo Inn | ALB YOUTH EDUCATION PROGRAM INFO TECH & VEH | 179000 | 179000 | 0% | Attempted for many years to solve anti-donation with NPO without success. UA will not pass AD, will use internally prior to reversion. | 6/30/2025 | 4/3/2024
Health, Housing, & Homelessness | 2023 | H2899 | Gateway Youth - San Mateo Inn | YOUTH SHELTER CONSTRUCT | 1542905 | 246491 | 84.02% | Remediation ongoing, demolition started, and design plans in process. Design underway for Phase 1, will be utilized for construction once design completed, construction proposals anticipated end of Feb 2025. Encumbered by NOO by March 2025 | 6/30/2027 | 11/28/2023
Health, Housing, & Homelessness - NPO | 2023 | H4070 | Gateway Youth - San Mateo Inn | Youth Temporary Living Facility Construction - Change to Purchase Youth Transitional Living Facility - Extend Time | 173250 | 74131.01 | 57.21% | ​Remediation ongoing, demolition started, and design plans in process. Design underway under 2023 grant and funding for Phase 1, will be utilized for construction once design completed, construction proposals anticipated end of Feb 2025. Encumbered by NOO by March 2025 | 6/30/2025 | 9/15/2023
Health, Housing, & Homelessness | 2024 | I2844 | Gateway Youth - San Mateo Inn | ALB YOUTH HSING NAVIGATION CAMPUS CONSTRUCT | 1163250 | 1163250 | 0% | ​Design underway under 2023 grant and funding for Phase 1, remediation and demolition currently underway. Will be utilized for construction once design completed, construction proposals anticipated end of Feb 2025. Encumbered by NOO by March 2025 | 6/30/2028 | 9/6/2024
Parks & Recreation | 2024 | I2743 | Geneivas Arroyo/Lowell Greenway | GENEIVAS ARROYO/LOWELL GREENWAY CONSTRUCT | 75000 | 75000 | 0% | NOO expected for 2025 for phase 1 trail work | 6/30/2028 | 8/20/2024
Municipal Development | 2021 | F2980 | Gibson Blvd. | GIBSON BLVD SE IMPROVE | 265000 | 61658 | 76.73% | ​Pending final NMDOT reimbursement, study completed. Remainder to be reauthorizing in 2025 session for scope and time. | 6/30/2025 | Received
Municipal Development | 2022 | G3117 | Girard Blvd. | GIRARD BLVD IMPROVE | 90000 | 0 | 100% | Waiting on NMDOT to approve NOO | 6/30/2026 | Received
Municipal Development | 2023 | H3299 | Girard Blvd. | GIRARD BLVD NE CONSTRUCT | 275000 | 0 | 100% | ​$3M in additional funds for construction required. Funds are encumbered, design is in progress. | 6/30/2027 | Received
Municipal Development | 2024 | I3256 | Girard Blvd. | GIRARD BLVD IMPROVE | 125000 | 125000 | 0% | ​Agreement received 10/28/24. design in process using previous capital outlay. Funds are insufficient to construct improvements, project requires approximately $3M to complete. | 6/30/2028 | 10/28/2024
Parks & Recreation | 2023 | H4041 | Gladiators | Indoor Arena Improvements - Change to Improve Albuquerque Playing Fields | 321750 | 321750 | 0% | Reauthorizing in 2025 session to give to state for use at Expo | 6/30/2026 | 10/24/2023
Parks & Recreation | 2022 | G2683 | Glenwood Hills Park | ALB GLENWOOD HILLS PK TENNIS COURTS REPAIR | 25000 | 0 | 100% | ​NOO expected 2025 for surfacing. | 6/30/2026 | 1/5/2023
Health, Housing, & Homelessness - NPO | 2021 | F2629 | God's Warehouse NPO | ALB MOBILE HOMELESS FCLTY VEH PRCHS | 110000 | 110000 | 0% | Need additional funds from G2730 for procurement. Waiting on Grant Agreement from the state. | 6/30/2025 | 3/6/2024
Health, Housing, & Homelessness - NPO | 2022 | G2730 | God's Warehouse NPO | ALB REFRIGERATED FOOD TRUCK PRCHS | 100000 | 100000 | Agreement not received from State | ​Waiting on Grant Agreement from the State - NPO spent several years accumulating funds for project. | 6/30/2026
Health, Housing, & Homelessness - NPO | 2023 | H2810 | God's Warehouse NPO | DISPLACED PERSONS VEH & EQUIP PRCHS | 101490 | 101490 | 0% | Waiting on Grant agreements from the State, need to clear Anti-donation rules. | 6/30/2025 | 11/11/2024
Health, Housing, & Homelessness - NPO | 2024 | I2759 | God's Warehouse NPO | KITCHEN FCLTY EQUIP & REN | 153450 | 153450 | 0% | Project requires additional funding. Need to address anti-donation concerns of facility ownership. | 6/30/2028 | 10/1/2024
Municipal Development | 2021 | F2981 | Golf Course & Ellison Bus Stop | ALB GOLF COURSE AT ELLISON BUS STOP CONSTRUCT | 18000 | 0 | 100% | Project Complete | 6/30/2025 | Received
Parks & Recreation - NPO | 2021 | F2613 | Greenhouse | ALB GREENHOUSE FACILITY IMPROVE | 95000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 12/10/2021
Parks & Recreation | 2024 | I2748 | Harwood Lateral Park | ALB HARWOOD LATERAL NORTH VALLEY PARK CONSTRUCT | 100000 | 100000 | 0% | NOO expected for 2025 for planning and design | 6/30/2028 | 8/22/2024
Parks & Recreation | 2024 | I2787 | Heritage Hills/Loma del Norte/Rotary Parks | PKS SHADE STRUCT INSTALL | 100000 | 100000 | 0% | NOO expected for 2025 shade construction | 6/30/2028 | 8/6/2024
Parks & Recreation | 2024 | I2749 | Highland Pool | HIGHLAND POOL REN | 247500 | 243925 | 1.444% | NOO expected in 2025 for additional pool improvements | 6/30/2028 | 8/22/2024
Senior Affairs | 2021 | F2011 | Highland Senior Center | ALB HIGHLAND SENIOR CTR REN | 79998 | 20658 | 74.18% | 11/21/24 CLOSE OUT PROJECT. This project complete. | 6/30/2025 | Received
Senior Affairs | 2023 | H2006 | Highland Senior Center | HIGHLAND SENIOR CTR - REN | 560000 | 560000 | Agreement not received from State | 11/21/24 Waiting for fully executed agreement from State ALTSD, | 6/30/2027
Senior Affairs | 2023 | H2007 | Highland Senior Center | HIGHLAND SENIOR CTR IMPROVE | 25000 | 25000 | Agreement not received from State | 11/21/24 Waiting for fully executed agreement from State ALTSD, | 6/30/2027
Senior Affairs | 2024 |  | Highland Senior Center |  | 371000 | 371000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Parks & Recreation | 2021 | F2614 | Holiday Park | ALB HOLIDAY PK PGRND EQUIP | 143400 | 0 | 100% | ​Project complete. Renovations at Holiday park. | 6/30/2025 | 9/9/2021
Arts & Culture - NPO | 2023 | H2823 | Holocaust Museum NPO | GENOCIDE & HOLOCAUST MUS IMPROVE | 175000 | 175000 | Agreement not received from State | ​Awaiting Use Agreement from NPO to meet anti-donation. | 6/30/2027
Arts & Culture - NPO | 2023 | H4035 | Holocaust Museum NPO | Holocaust and Intolerance Museum - Extend Time | 823898 | 662075 | 19.64% | These funds will be released pending the organization's relocation into a new site, recently identified. | 6/30/2025 | 9/15/2023
Arts & Culture - NPO | 2024 | I2744 | Holocaust Museum NPO | ALB GENOCIDE CONSTRUCT | 915250 | 915250 | 0% | The organization has identified a site and these funds will soon be encumbered. | 6/30/2028 | 9/6/2024
Health, Housing, & Homelessness - NPO | 2021 | F2592 | Homewise NPO | ALB CMTY KITCHEN CONSTRUCT | 205000 | 205000 | Agreement not received from State | ​Waiting on Scope of Services from Non-profit Organization to form Use Agreement to pass anti-donation. | 6/30/2025
Arts & Culture | 2024 | I2751 | IDL Outdoor Glass Mosaic | INTL DIST LIB GLASS MOSAIC INSTALL | 125000 | 125000 | 0% | Pending input from library staff and community members on design and location. Installation will begin in early 2025 | 6/30/2028 | 9/6/2024
Parks & Recreation | 2024 | I2750 | Indoor Track Facility | ALB INDOOR TRACK FCLTY CONSTRUCT | 25000 | 25000 | 0% | NOO expected for 2025 track improvements after the 2025 season | 6/30/2028 | 8/22/2024
Arts & Culture | 2021 | F2615 | International District Library | ALB INTERNATIONAL DISTRICT LIBRARY IMPROVE | 241000 | 0 | 100% | Funding is fully encumbered for materials. Awaiting reimbursement. | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2687 | International District Library Park | ALB INTRNATL DIST LIB PK DVLP | 450000 | 450000 | 0% | NOO expected in 2025 for Phase 1 construction in 2025 | 6/30/2026 | 12/29/2022
Parks & Recreation | 2023 | H2827 | International District Library Park | INTRNATL DIST LIB PK CONSTRUCT | 351490 | 351490 | 0% | NOO expected early 2025 for park construction. | 6/30/2027 | 10/11/2023
Metropolitan Redevelopment | 2023 | H2828 | International District MRA | INTRNATL DIST METRO REDVLP AREA DVLP | 1965000 | 194350 | 90.11% | ​MRA is in contact with the owner of Walgreens but has not been able to negotiate a deal. Discussions are continuing. If Walgreens is not a possibility, MRA will explore other improvements in the Central/Highland/Upper Nob Hill MRA, to include public improvements such as lighting and traffic calming. | 6/30/2027 | 10/11/2023
General Services | 2022 | G2688 | Isotopes | ALB ISOTOPES STADIUM IMPROVE | 175000 | 0 | 100% | ​Project complete. Upgrades made to Isotopes stadium. | 6/30/2026 | 12/29/2022
General Services | 2023 | H2829 | Isotopes | ISOTOPES PK IMPROVE | 100000 | 100000 | Agreement not received from State | ​Waiting on LGD for Grant Agreement | 6/30/2027
Municipal Development | 2022 | G2686 | ITS | ALB INTELLIGENT TRANSPORTATION SYSTEM IMPROVE | 25000 | 0 | 100% | Waiting on LGD to approve NOO | 6/30/2026 | 9/7/2022
Youth & Family Services | 2021 | F2617 | Jack Candelaria Community Center | ALB JACK CANDELARIA COMMUNITY CENTER REN | 495000 | 0 | 100% | Under construction. 75% complete | 6/30/2025 | 9/22/2021
Youth & Family Services | 2022 | G2739 | Jack Candelaria Community Center | ALB SOUTH SAN JOSE PARK & CMTY CTR IMPROVE | 2200000 | 0 | 100% | Under construction 75% complete | 6/30/2026 | 1/23/2023
Youth & Family Services | 2023 | H2830 | Jack Candelaria Community Center | J. CANDELARIA CMTY CTR BOXING FCLTY IMPROVE | 200000 | 0 | 100% | Under construction. 75% complete | 6/30/2027 | 10/11/2023
Parks & Recreation | 2021 | F2618 | Jerry Cline Tennis Center | ALB JERRY CLINE TENNIS CENTER REN | 85000 | 0 | 100% | ​Construction Complete. Awaiting processing of final invoice. | 6/30/2025 | 9/9/2021
Parks & Recreation | 2022 | G2689 | Jerry Cline Tennis Center | ALB JERRY CLINE TENNIS CENTER DVLP | 210000 | 0.98 | 100% | ​Construction nearly complete. Anticipate completion by end of December 2024. | 6/30/2026 | 9/7/2022
Parks & Recreation | 2024 | I2752 | Jerry Cline Tennis Center | ALB JERRY CLINE TENNIS CTR REN | 100000 | 100000 | 0% | ​NOO expected in 2025 for tennis court improvements | 6/30/2028 | 10/1/2024
Youth & Family Services | 2022 | G2690 | Joan Jones Community Center | ALB JOAN JONES CMTY CTR CONSTRUCT | 75000 | 0 | 100% | Project under construction | 6/30/2026 | 1/17/2023
Youth & Family Services | 2023 | H2831 | Joan Jones Community Center | JOAN JONES CMTY CTR IMPROVE | 200000 | 0 | 100% | Project under construction | 6/30/2027 | 10/11/2023
Youth & Family Services | 2024 | I2753 | Joan Jones Community Center | JOAN JONES CMTY CTR CONSTRUCT | 25000 | 25000 | 0% | Waiting on quote from vendor. | 6/30/2028 | 9/6/2024
Health, Housing, & Homelessness - NPO | 2022 | G2755 | John Marshal HSSC | ALB WREHSE & VEH PRCHS | 120399 | 120399 | Agreement not received from State | Non profit not responsive. Will use for John Marshal HSSC | 6/30/2026
Health, Housing, & Homelessness | 2024 | I2755 | John Marshall HSSC Kitchen Renovation | JOHN MARSHALL HSSC KITCHENS REN | 648450 | 648450 | 0% | Quote for project is estimated at $800k. Project will require additional $145K to complete. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2023 | H2832 | Juan Tabo Hills Park | JUAN TABO HILLS PARK PH 3 CONSTRUCT | 125000 | 125000 | 0% | NOO expected December 2024 for park construction spring 2025. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2757 | Juan Tabo Hills Park | ALB JUAN TABO HILLS PK PH 3 CONSTRUCT | 25000 | 25000 | 0% | NOO expected December 2024 for park construction spring 2025. | 6/30/2028 | 8/22/2024
Parks & Recreation | 2021 | F2619 | Juan Tabo Hills Park - Dog Park | ALB JUAN TABO HILLS PK PLAN | 30000 | 7156.39 | 76.15% | NOO Expected December 2024 - January 2025 for dog park construction. | 6/30/2025 | 9/22/2021
Parks & Recreation | 2022 | G2691 | Juan Tabo Hills Park - Dog Park | ALB JUAN TABO HILLS PK PH 3 CONSTRUCT | 400000 | 290402.3 | 27.4% | NOO expected December 2024 - January 2025 for dog park construction. | 6/30/2026 | 1/9/2023
Municipal Development | 2023 | H3288 | Juan Tabo Storm Drainage | JUAN TABO STORM DRAIN FCLTY DES | 125000 | 0 | 100% | ​NOO issued by NMDOT; design in progress. Project is significantly underfunded. Project to be developed in 4 or 5 phases as total construction cost exceeds $25M. | 6/30/2027 | Received
Municipal Development | 2024 | I3249 | Juan Tabo Storm Drainage | ALB JUAN TABO STORM DRAIN DESIGN | 175000 | 175000 | 0% | Design in process using previously issued capital outlay. Funds are insufficient to proceed to construction. | 6/30/2028 | Received
Parks & Recreation | 2024 | I2756 | Juan Tabo Trail Connection To KAFB Construct | JUAN TABO BIKE TRAIL CONNECTION TO KAFB CONSTRUCT | 140000 | 140000 | 0% | NOO expected in 2025 for design | 6/30/2028 | 8/22/2024
Arts & Culture - NPO | 2024 | I2852 | Keshet Dance Center - NPO | Mentoring Center | 326700 | 326700 | 0% | This is a grant recently transferred from MRCOG for Keshet Dance Company, have begun work on creating Use Agreement for Anti-Donation. | 6/30/2028 | 10/23/2024
Parks & Recreation | 2024 | I2758 | Kirtland Park | KIRTLAND PK IMPROVE | 100000 | 100000 | 0% | NOO expected in 2025 for improvements | 6/30/2028 | 8/22/2024
Parks & Recreation | 2024 | I4024 | Kirtland Park | Kirtland Park | 50000 | 50000 | 0% | NOO expected mid 2025 for late 2025 construction | 6/30/2027 | 9/6/2024
Arts & Culture | 2022 | G2692 | Kirtland Park Mural | ALB KIRTLAND PK/THOMAS BELL CMTY CTR MURAL REPAIR | 20000 | 0 | 100% | Funding is fully encumbered and contract has been executed with artist. | 6/30/2026 | 1/17/2023
Parks & Recreation | 2024 | I2760 | Krogh Park | ALB KROGH PK IMPROVE | 100000 | 100000 | 0% | NOO expected in 2025 for playground improvements | 6/30/2028 | 8/22/2024
Parks & Recreation | 2021 | F2620 | Ladera Golf Course | ALB LADERA GOLF COURSE IMPROVE | 525000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 9/9/2021
Parks & Recreation | 2023 | H2835 | Ladera Golf Course | LADERA GOLF COURSE IMPROVE | 200000 | 43309.37 | 78.35% | Encumbered for lighting | 6/30/2027 | 110/11/2023
Parks & Recreation | 2024 | I2761 | Ladera Golf Course | LADERA GOLF COURSE IMPROVE | 185000 | 0 | 100% | Fully encumbered for lighting improvements. | 6/30/2028 | 8/22/2024
Parks & Recreation | 2023 | H2836 | Lauren C. Boles Park | LAUREN C BOLES PK TENNIS COURTS IMPROVE | 180000 | 9073.15 | 94.96% | NOO obtained fall 2024. Project will complete 2025. | 6/30/2027 | 10/11/2023
Municipal Development | 2021 | F2982 | Lead & Coal | LEAD AVE SE & COAL AVE SE IMPROVE | 300000 | 0 | 100% | Waiting on reimbursement from NMDOT, project complete. | 6/30/2025 | Received
Municipal Development | 2022 | G3118 | Lead & Coal | LEAD AVE AND COAL AVE UPGRADE | 300000 | 0 | 100% | ​Funds encumbered and study underway. Once completed recommended improvements will be evaluated against funding available | 6/30/2026 | Received
Municipal Development | 2023 | H3300 | Lead & Coal | LEAD AVE SE & COAL AVE SE IMPROVE | 576490 | 576490 | 0% | ​Pending completion of study being conducted using prior grant appropriation in order to determine next steps | 6/30/2027 | Received
Parks & Recreation - NPO | 2021 | F2621 | Lobo Little League | ALB LOBO LL BALDUINI PARK IMPROVE | 50000 | 0 | 100% | PROJECT COMPLETE | 6/30/2025 | 8/26/2022
Parks & Recreation - NPO | 2022 | G2682 | Lobo Little League | ALB GILBERT P. SANCHEZ PARK CONSTRUCT | 25000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2026 | Received
Parks & Recreation - NPO | 2022 | G2694 | Lobo Little League | ALB LOBO LL IMPROVE | 70000 | 0 | 100% | Project under construction. Completion expected 2025. | 6/30/2026 | 1/9/2023
Parks & Recreation - NPO | 2024 | I2747 | Lobo Little League | GILBERT P. SANCHEZ PK IMPROVE | 100000 | 100000 | 0% | NOO expected in 2025 for field improvements | 6/30/2028 | 8/20/2024
Youth & Family Services | 2023 | H2837 | Loma Linda Community Center | LOMA LINDA CMTY CTR IMPROVE | 297000 | 297000 | 0% | Phase 1 under construction. This funding will be used for Phase 2 | 6/30/2027 | 10/11/2023
Youth & Family Services | 2024 | I2762 | Loma Linda Community Center | LOMA LINDA CMTY CTR IMPROVE | 430000 | 430000 | 0% | Will submit NoO. | 6/30/2028 | 9/6/2024
Arts & Culture | 2021 | F2622 | Lomas Tramway Library | ALB RPLC LIB ROOF Lomas Tramway HVAC REN | 625000 | 122030.42 | 80.48% | This project is underway and completion is expected in 2025. | 6/30/2025 | 10/6/2021
Arts & Culture | 2023 | H2838 | Lomas Tramway Library | LOMAS TRAMWAY LIBRARY REN | 519750 | 519750 | 0% | Project is in the planning process and renovation phases will begin in 2025 | 6/30/2027 | 10/11/2023
Arts & Culture | 2024 | I2763 | Lomas Tramway Library | LOMAS TRAMWAY LIB IMPROVE | 175000 | 165956 | 5.168% | Pending scope and fees, NoO will be submitted | 6/30/2028 | 9/6/2024
Parks & Recreation | 2022 | G2695 | Los Altos Golf Course | ALB LOS ALTOS GOLF COURSE IMPROVE | 50000 | 50000 | 0% | NOO expected December 2024 for shade installation 2025 | 6/30/2026 | 1/6/2023
Parks & Recreation | 2024 | I2764 | Los Altos Golf Course | LOS ALTOS GOLF COURSE IMPROVE | 50000 | 50000 | 0% | NOO expected December 2024 for shade installation 2025 | 6/30/2028 | 8/22/2024
Parks & Recreation | 2021 | F2623 | Los Altos Park | ALB LOS ALTOS PK REN | 1440000 | 0 | 100% | ​Project complete. Improvements to Los Altos park. | 6/30/2025 | Received
Parks & Recreation | 2022 | G2696 | Los Altos Park | ALB LOS ALTOS PARK REN | 725000 | 0 | 100% | Project under construction. Completion expected early 2025. | 6/30/2026 | 9/7/2022
Parks & Recreation | 2023 | H2839 | Los Altos Park | LOS ALTOS PARK IMPROVE | 950000 | 0 | 100% | ​Currently in construction with anticipated completion in 2025. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2765 | Los Altos Park – Phase 2 | LOS ALTOS PK PH 2 CONSTRUCT | 50000 | 50000 | 0% | NOO expected in 2025 for immediate construction. | 6/30/2028 | 8/22/2024
Arts & Culture | 2023 | H2840 | Los Griegos Library | LOS GRIEGOS LIBRARY REN | 50000 | 50000 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2027 | 11/3/2023
Parks & Recreation | 2022 | G2697 | Los Tomases Park | ALB LOS TOMASES PARK REN | 280000 | 0 | 100% | ​PROJECT COMPLETE. | 6/30/2026 | 1/9/2023
Senior Affairs | 2022 | G2003 | Los Volcanes Senior Center | ALB LOS VOLCANES SENIOR CTR REN | 425700 | 0 | 100% | 11/21/24 CLOSE OUT PROJECT. This grant is fully executed and project complete. | 6/30/2026 | Received
Senior Affairs | 2023 | H2008 | Los Volcanes Senior Center | LOS VOLCANES SENIOR CTR IMPROVE | 250000 | 250000 | 0% | 11/21/24 Received fully executed grant agreement, obtaining quote from Weil Construction for rehab of ADA ramp and will submit NOO to State for approval to proceed to expend all funds. | 6/30/2027 | Received
Senior Affairs | 2024 | I2010 | Los Volcanes Senior Center | ALB LOS VOLCANES SENIOR CTR IMPROVE | 300000 | 300000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Senior Affairs | 2024 |  | Los Volcanes Senior Center Equipment |  | 60000 | 60000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Arts & Culture | 2023 | H2841 | Main Library | MAIN LIBRARY REN | 100000 | 43687 | 56.31% | This project is underway and completion is expected in 2025. | 6/30/2027 | 10/11/2023
Arts & Culture | 2024 | I2766 | Main Library | MAIN LIB REN | 148500 | 148500 | 0% | The HVAC upgrade project for the Main Library is currently pending full funding. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2021 | F2624 | Maloof Air Park | ALB MALOOF AIR FIELD REN | 37000 | 12339.65 | 66.65% | NOO expected late 2024 early 2025. | 6/30/2025 | 11/1/2021
Parks & Recreation | 2022 | G2698 | Maloof Air Park | ALB MALOOF AIR PK IMPROVE | 90000 | 90000 | 0% | NOO expected December 2024, for shade and solar panels | 6/30/2026 | 1/17/2023
Parks & Recreation | 2023 | H3259 | Maloof Air Park | MALOOF MEM AIR PK IMPROVE | 163350 | 163350 | 0% | NOO expected in 2025 for improvements at the airpark | 6/30/2027 | 11/28/2023
Parks & Recreation | 2024 | I2767 | Maloof Air Park | ALB MALOOF AIR PK IMPROVE | 150000 | 150000 | 0% | NOO expected in 2025 for additional improvements to the airpark | 6/30/2028 | 8/3/2024
Senior Affairs | 2021 | F2012 | Manzano Mesa Multigen | ALB MANZANO MESA MULTIGENERATIONAL CTR EQUIP | 21582 | 0 | 100% | 11/21/24 CLOSE OUT PROJECT. This grant is fully executed and project complete. | 6/30/2025 | Received
Senior Affairs | 2023 | H2843 | Manzano Mesa Multigen | MANZANO MESA MULTIGENERATIONAL CTR SEC SYS IMP | 25000 | 25000 | 0% | 11/21/24 obtaining revised quotes to expend all funds. | 6/30/2027 | 10/31/2023
Senior Affairs | 2024 |  | Manzano Mesa Multigen |  | 181000 | 181000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Parks & Recreation | 2021 | F2625 | Manzano Mesa Pickleball | ALB MANZANO MESA PICKLE BALL COMPLEX REN | 455400 | 73.18 | 99.98% | ​Major construction project completed. Reviewing options to use remaining funding. | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2699 | Manzano Mesa Pickleball | ALB MANZANO MESA PICKLEBALL FCLTY DVLP | 960300 | 0 | 100% | ​PROJECT COMPLETE. | 6/30/2026 | 1/10/2023
Parks & Recreation | 2023 | H2842 | Manzano Mesa Pickleball | MANZANO MESA CTR PICKLEBALL CT CONSTRUCT | 695772 | 0 | 100% | Project Complete. Funding used to construct the new pickleball courts at Manzano Mesa. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2768 | Manzano Mesa Pickleball | MANZANO MESA PICKLEBALL CMPLX REN | 565000 | 557053 | 1.407% | NOO expected in 2025 for design and later in 2026 for construction | 6/30/2028 | 8/3/2024
Parks & Recreation | 2022 | G2700 | Marion L. Fox Park | ALB MARION L. FOX MEMORIAL PARK REN | 75000 | 75000 | 0% | NOO expected in 2025 for park improvements, along with H2844 | 6/30/2026 | 1/6/2023
Parks & Recreation | 2023 | H2844 | Marion L. Fox Park | MARION L. FOX MEM PK IMPROVE | 151490 | 151490 | 0% | NOO expected in 2025 for construction of park improvements, along with G2700 | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2769 | Marion L. Fox Park | ALB MARION L. FOX MEM PK UPGRADE | 125000 | 125000 | 0% | NOO expected in 2025 for improvements | 6/30/2028 | 8/3/2024
Parks & Recreation | 2022 | G2701 | Mariposa Basin Park | ALB MARIPOSA PK POND REN | 50000 | 0 | 100% | NOO issued September 2024; construction is in progress at the pond | 6/30/2026 | 1/6/2023
Parks & Recreation | 2023 | H2845 | Mariposa Basin Park | MARIPOSA BASIN PK IMPROVE | 185000 | 185000 | 0% | NOO expected for 2025 for additional pond improvements | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2770 | Mariposa Basin Park | MARIPOSA BASIN PK GARDEN IMPROVE | 150000 | 4587.01 | 96.94% | NOO expected in 2025 for improvements | 6/30/2028 | 8/3/2024
Senior Affairs | 2024 | I2772 | Martineztown Multigenerational Center | ALB MARTINEZTOWN MULTIGENERATIONAL CTR EQUIP | 200000 | 200000 | 0% | 10/25/24 Waiting on state for award letter from ALTSD | 6/30/2028 | 9/11/2024
Parks & Recreation | 2021 | F2626 | Matheson Park | ALB MATHESON PK PGRND EQUIP | 130000 | 3 | 100% | ​PROJECT COMPLETE. | 6/30/2025 | 10/13/2021
Parks & Recreation | 2022 | G2702 | Matheson Park | ALB MATHESON PARK SECURITY & LIGHT INSTALL | 16000 | 16000 | 0% | ​NOO expected in 2025 for solar lighting | 6/30/2026 | 1/6/2023
Municipal Development | 2024 | I3257 | Matthew Ave Repairs | MATTHEW AVE NW REN | 50000 | 50000 | 0% | Agreement Received 11/14/2024, pending quotes from contractors. | 6/30/2028 | 11/14/2024
Parks & Recreation - NPO | 2022 | G2703 | McKinley Bike Shop | ALB MCKINELY BIKE SAFETY & ED CTR REN | 75000 | 67633.07 | 9.823% | NOO issued November 2024 for design; balance to be used for phase 2 construction 2025 | 6/30/2026 | 10/19/2023
Parks & Recreation - NPO | 2023 | H2883 | McKinley Bike Shop | TEEN & YOUTH CTRS REN | 425000 | 425000 | Agreement not received from State | Waiting on Grant Agreement from LGD - phase 2 anticipated in 2026 | 6/30/2027
Parks & Recreation - NPO | 2023 | H2898 | McKinley Bike Shop | YOUTH PROGRAMS FCLTY REN | 1080575 | 652012.25 | 39.66% | NOO expected in 2025 for design and 2026 for phase 2 building improvements | 6/30/2027 | 12/12/2023
Municipal Development | 2021 | F2983 | McMahon | ALB MCMAHON EXPAND NORTHWEST EXPAND | 150000 | 0 | 100% | ​Waiting on NOO approval from NMDOT. Changed project parameters due to lack of full funding. Needs additional $4M for complete funding. | 6/30/2025 | Received
Municipal Development | 2022 | G3119 | McMahon | MCMAHON BLVD NW IMPROVE | 200000 | 200000 | 0% | Changed project parameters due to lack of full funding. Needs additional $4M for completer funding. Funding now to be used to purchase lighting once design is complete. | 6/30/2026 | Received
Municipal Development | 2023 | H4060 | McMahon | MCMAHON BLVD IMPROVE BERN CO | 300000 | 45639 | 84.79% | ​Agreement received 11/14/2024. Design is 90% complete; ROW and utility coordination with PNM is in process. Reauthorization agreement has been executed and grant expenses and reimbursements are being prepared under to newly reauthorized agreement. | 6/30/2025 | 11/14/2024
Municipal Development | 2024 | I4043 | McMahon | McMahon Boulevard Improvement - Extend Time | 300000 | 103328 | 65.56% | ​Funds were reauthorized to extend time under grant I4043. NMDOT took over one year to issue the new grant agreement NOO was issued under grant E2818 in the amount of $196K. Remaining money to be combined with McMahon lighting phase G3119. | 6/30/2026 | Received
Municipal Development | 2021 | F2976 | Medians | ALB ROADS MEDIAN LANDSCAPING CONSTRUCT | 60000 | 60000 | 0% | ​Currently in design, construction complete by March 2026. | 6/30/2025 | Received
Municipal Development | 2022 | G3120 | Mesa del Sol Blvd. | MESA DEL SOL BLVD CONSTRUCT | 100000 | 100000 | 0% | Pending NMDOT determination on location of the I-25/Mesa del Sol Interchange. Funds not sufficient to initiate scope. | 6/30/2026 | Received
Municipal Development | 2022 | G2305 | Mesa del Sol Lift Stations | ALB MDS EAST PLAT LIFT STATION CONSTRUCT | 50000 | 50000 | 0% | ​COA will Reauth in 2025 Session to transfer grant to Water Utility Authority. | 6/30/2026 | Received
Municipal Development | 2022 | G2306 | Mesa del Sol Lift Stations | ALB MESA DEL SOL NORTH PLAT LIFT STATION CONSTRUCT | 50000 | 50000 | 0% | ​COA will Reauth in 2025 Session to transfer grant to Water Utility Authority. | 6/30/2026 | Received
Municipal Development | 2023 | H2825 | Mesa del Sol Lift Stations | INFRA & MESA DEL SOL LIFT STN CONSTRUCT | 200000 | 200000 | 0% | ​COA will Reauth in 2025 Session to transfer grant to Water Utility Authority. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2021 | F2628 | Mesa Verde Park | ALB MESA VERDE PK REN | 20000 | 0 | 100% | PROJECT COMPLETE | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2704 | Mesa Verde Park | ALB MESA VERDE PARK REN | 150000 | 137371.53 | 8.419% | NOO expected in 2025 for additional design | 6/30/2026 | 1/17/2023
Parks & Recreation | 2024 | I2773 | Mesa Verde Park | ALB MESA VERDE PK REN | 125000 | 125000 | 0% | NOO December 2025 for design. | 6/30/2028 | 8/3/2024
Parks & Recreation - NPO | 2023 | H2848 | Mile High Little League | MILE HIGH LL FCLTY IMPROVE | 366300 | 366300 | 0% | NOO expected in 2025 for league improvements | 6/30/2027 | 10/11/2023
Parks & Recreation - NPO | 2024 | I2774 | Mile High Little League | MILE HIGH LL FCLTY IMPROVE | 450000 | 450000 | 0% | NOO expected in 2025 for field and league improvements | 6/30/2028 | 8/3/2024
Municipal Development | 2023 | H4057 | MLK Welcome Signs | Dr. Martin Luther King, Jr. Avenue Welcome Sign Construction - Change to Construct Lighting | 15000 | 15000 | 0% | ​Agreement received 11/12/24 - Quote from lighting vendor due 12/31/24, DFA NOO upon receipt. | 6/30/2027 | 11/25/2024
Municipal Development | 2022 | G3121 | Montano Rd. Medians | MONTANO RD NW LNDSCP IMPROVE | 39769 | 39769 | 0% | ​Proposal requested from vendor, due by 12/1/24. NOO to be requested upon receipt of proposal. | 6/30/2026 | Received
Municipal Development | 2024 | I3258 | Monte Vista Blvd | MONTE VISTA BLVD NE UPGRADE | 45000 | 45000 | 0% | ​Agreement received 10/28/24. Medians are proceeding to construction and once that is completed capital outlay funds to be used for the landscaping component of the project | 6/30/2028 | 10/28/2024
Parks & Recreation | 2022 | G2706 | Montgomery Pool | ALB MONTGOMERY POOL IMPROVE | 925000 | 800797.91 | 13.43% | Currently in design. 100% CDs anticipated by end of December 2024. | 6/30/2026 | 2/17/2023
Parks & Recreation | 2023 | H2849 | Montgomery Pool | MONTGOMERY POOL REN | 25000 | 25000 | 0% | NOO expected in 2025 for improvements in 2025 | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2775 | Montgomery Pool | MONTGOMERY POOL REN | 25000 | 25000 | 0% | NOO expected in 2025 for improvements in 2025 | 6/30/2028 | 8/3/2024
Parks & Recreation | 2021 | F2630 | Morningside Park | ALB MORNINGSIDE PK REN | 50000 | 0 | 100% | Project in construction. To be complete in Spring 2025. | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2707 | Morningside Park | ALB MORNINGSIDE PARK EQUIP CONSTRUCT | 250000 | 0 | 100% | NOO submitted in November 2024 for construction. Waiting on state approval | 6/30/2026 | 12/29/2022
Parks & Recreation | 2023 | H2850 | Morningside Park | MORNINGSIDE PARK IMPROVE | 250000 | 163759.57 | 34.5% | Project in construction. To be complete in Spring 2025. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2776 | Morningside Park | ALB MORNINGSIDE PK UPGRADE | 350000 | 350000 | 0% | Project in construction. To be complete in Spring 2025. | 6/30/2028 | 8/3/2024
Municipal Development | 2023 | H3301 | Mountain & Edith | MOUNTAIN RD AND EDITH BLVD IMPROVE | 50000 | 50000 | 0% | ​$4M in additional funding is needed for right of way activities and construction of the proposed improvements. Design is underway using previous capital outlay. | 6/30/2027 | Received
Health, Housing, & Homelessness - NPO | 2022 | G2710 | New Day NPO | ALB NEW DAY HMLS FCLTY FENCE INSTALL | 45000 | 45000 | Agreement not received from State | Waiting on Grant agreements from the State, need to clear Anti-donation rules. | 6/30/2026
Health, Housing, & Homelessness - NPO | 2022 | G2711 | New Day NPO | ALB NEW DAY MLTPRPS CTR FENCE INSTALL | 35000 | 35000 | Agreement not received from State | Waiting on Grant agreements from the State, need to clear Anti-donation rules. | 6/30/2026
Parks & Recreation | 2021 | F2636 | New Mexico Veterans Memorial Park | ALB NM VETERANS MEMORIAL PK REN | 937600 | 737148 | 21.38% | ​Project currently in design in preparation for construction. | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2712 | New Mexico Veterans Memorial Park | ALB NM VETERANS MEM IMPROVE | 175000 | 175000 | 0% | ​NOO expected in late 2024 | 6/30/2026 | 1/5/2023
Parks & Recreation | 2024 | I2779 | New Mexico Veterans Memorial Park | ALB NM VETERANS' MEM PK IMPROVE | 60000 | 60000 | 0% | NOO expected in 2025 for park improvements | 6/30/2028 | 8/3/2024
Office of Equity & Inclusion - NPO | 2024 | I2697 | NM Black Excellence NPO | ADMIN YOUTH PGRM HEADQUARTERS EQUIP | 90000 | 90000 | 0% | Waiting on Scope of Services from NPO to form Use Agreement to meet anti-donation. | 6/30/2026 | 9/6/2024
Youth & Family Services - NPO | 2022 | G2658 | NM Black Leadership Council NPO | ALB BLDG INTRNATL DIST FCLTY ACQ | 100000 | 100000 | Agreement not received from State | CIP working with LGD & DFA to remove Special Conditions | 6/30/2026
Youth & Family Services - NPO | 2024 | I2695 | NM Girl Scouts NPO | VAN PRCHS | 65000 | 65000 | 0% | Non-profit providing exhibits for Use Agreement to meet anti-donation. | 6/30/2026 | 9/6/2024
Municipal Development | 2024 | H2121-2402 | Nob Hill Main Street | Nob Hill Main Street | 114000 | 5834.3 | 94.88% | PO issued and equipment ordered. Vendor anticipates deliver around end of Jan 2025, with project completion around end of Feb 2025. | 6/30/2027 | 8/22/2024
Arts & Culture - NPO | 2021 | F2633 | North 4th NPO | ALB N FOURTH ART CTR REN | 350000 | 93902 | 73.17% | The security project is complete, and the City is working with current tenant to identify additional facility needs. | 6/30/2025 | 6/8/2022
Arts & Culture - NPO | 2022 | G2675 | North 4th NPO | ALB FILM/MEDIA TRAIN EQUIP | 100000 | 100000 | Agreement not received from State | ​A reauthorization of these funds will be requested due to the third party originally associated with this project no longer being involved. The use agreement requires an update to redirect the funds towards the Sawmill project. | 6/30/2026
Parks & Recreation | 2021 | F2632 | North Domingo Baca Aquatic Center | ALB N DOMINGO BACA AQUATIC CTR CONSTRUCT | 2740000 | 0 | 100% | ​Contract awarded. Currently in construction for Base Bid scope. Phase I of the project is currently in construction. Phase I includes infrastructure and mechanical building but lacks the indoor swimming pool. Phase II (indoor pool) currently needs an additional 15M-20M for construction. | 6/30/2025 | 10/28/2021
Parks & Recreation | 2022 | G2713 | North Domingo Baca Aquatic Center | ALB NORTH DOMINGO BACA POOL CONSTRUCT | 3940000 | 0 | 100% | ​PROJECT COMPLETE. Additional scope being completed with other funding. Phase I of the project is currently in construction. Phase I includes infrastructure and mechanical building but lacks the indoor swimming pool. Phase II (indoor pool) currently needs an additional 15M-20M for construction. | 6/30/2026 | 12/29/2022
Parks & Recreation | 2023 | H2852 | North Domingo Baca Aquatic Center | N DOMINGO BACA PK AQUATIC CTR CONSTRUCT | 6103350 | 0 | 100% | NOO expected in 2025 for pool development. Phase I of the project is currently in construction. Phase I includes infrastructure and mechanical building but lacks the indoor swimming pool. Phase II (indoor pool) currently needs an additional 15M-20M for construction. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2854 | North Domingo Baca Aquatic Center | NORTH DOMINGO BACA AQUATIC CTR CONSTRUCT | 1050000 | 0 | 100% | Phase I of the project is currently in construction. Phase I includes infrastructure and mechanical building but lacks the indoor swimming pool. Phase II (indoor pool) currently needs an additional 15M-20M for construction. | 6/30/2028 | 8/3/2024
Senior Affairs | 2023 | H2009 | North Domingo Baca Multigen | NORTH DOMINGO BACA MULTIGENERATIONAL CENTER | 65000 | 65000 | 0% | 11/21/24 Waiting for fully executed agreement from ALTSD, Obtained quote from National Restaurant Supply, will submit NOO to state for purchase approval. | 6/30/2027 | Received
Senior Affairs | 2024 |  | North Domingo Baca Multi-gen Equipment |  | 90000 | 90000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Senior Affairs | 2024 |  | North Domingo Baca Multi-gen Vehicles |  | 120000 | 120000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Parks & Recreation | 2024 | I2778 | North Domingo Baca Park | ALB N DOMINGO BACA PK ENTRYWAY REN | 20000 | 20000 | 0% | NOO expected in 2025 for park improvements | 6/30/2028 | 8/3/2024
Parks & Recreation | 2022 | G2714 | North Valley Dog Park | ALB NORTH VALLEY DOG PARK CONSTRUCT | 25000 | 11008.75 | 55.96% | NOO expected in early 2025 for design | 6/30/2026 | 1/5/2023
Senior Affairs | 2023 | H2010 | North Valley Senior Center | NORTH VALLEY SENIOR CTR - REN | 200000 | 200000 | 0% | 10/22/24 Waiting for fully executed agreement from ALTSD, Obtained quote from National Restaurant Supply, will submit NOO to state for purchase approval. | 6/30/2027 | Received
Senior Affairs | 2024 |  | North Valley Senior Center Equipment |  | 55000 | 55000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Albuquerque Police Department | 2021 | F2635 | Northeast Area Command | ALB NE AREA COMMAND POLICE SUBSTATION IMPROVE | 250000 | 0 | 100% | Fully encumbered | 6/30/2025 | 10/6/2021
Albuquerque Police Department | 2022 | G2715 | Northeast Area Command | ALB NORTHEAST AREA COMMAND POLICE STN REN | 200000 | 0 | 100% | Fully encumbered | 6/30/2026 | 1/5/2023
Albuquerque Police Department | 2023 | H2853 | Northeast Area Command | NE AREA POLICE STN IMPROVE | 198000 | 174324 | 11.96% | Parking lot is in process of being upgraded.​Working with Council staff to spend down remaining funds, scope and fee expected by 12/30/24 | 6/30/2027 | 10/11/2023
Albuquerque Police Department | 2024 | I2790 | Northeast Area Command | POLICE DEPT NE AREA COMMAND REN | 120000 | 120000 | 0% | Planning in process. APD Grant Admin is working with Facilities Coordinator to create spending plan. | 6/30/2028 | 9/9/2024
Municipal Development | 2023 | H3289 | Northeast Medians | NE MEDIANS IMPROVE | 300000 | 204015 | 31.99% | ​Design & ROW completion underway, will proceed to construction once complete. | 6/30/2027 | Received
Albuquerque Fire Rescue | 2023 | H4033 | Northwest Fire Station | Fire Station 23 Construction - Change to construct a Fire Station | 247500 | 247500 | 0% | Awaiting quote from contractor for HVAC at FS21, NOO to be requested upon receipt. | 6/30/2025 | 10/26/2023
Metropolitan Redevelopment - NPO | 2022 | G2716 | Nuevo Atrisco | ALB NUEVO ATRISCO PLAZA PH 2 CONSTRUCT | 1150000 | 0 | 100% | ​Fully expended | 6/30/2026 | 2/1/2023
Municipal Development | 2022 | G3122 | Odelia Rd. | ODELIA RD NE SAFETY IMPROVE CONSTRUCT | 25000 | 25000 | 0% | ​State would not allow the purchase of equipment. Quote is being requested from striping on call contractor for the intersection of University/Odelia/Indian School, due 12/31/24. Once received revised NOO to be submitted to NMDOT | 6/30/2026 | Received
Parks & Recreation | 2024 | I2782 | Old Town Plaza | OLD TOWN PLAZA | 150000 | 150000 | 0% | NOO expected in 2025 for design and 2026 for improvements | 6/30/2028 | 8/3/2024
Parks & Recreation | 2024 | I2783 | Open Space City-Wide Sign Plan | ALB OPEN SPACE SIGNAGE INSTALL | 120000 | 120000 | 0% | NOO expected in 2025 for sign installation | 6/30/2028 | 8/3/2024
Arts & Culture - NPO | 2023 | H2884 | Opera Southwest NPO | THEATRICAL EQUIPMENT PRCHS | 510000 | 510000 | 0% | Agreement Received 11/20/24, obtaining quotes from vendors. | 6/30/2027 | 11/20/2024
Parks & Recreation | 2024 | I2784 | Ouray Dog Park Improvements | ALB OURAY DOG PK IMPROVE | 50000 | 50000 | 0% | NOO expected in 2025 for dog park improvements | 6/30/2028 | 8/3/2024
Municipal Development | 2023 | H4061 | Ouray Rd. | Ouray Road NW and 57th Street NW Median Construction - Extend Time | 318250 | 5237 | 98.35% | ​Project was previously issued NOO by DOT for construction. Construction is complete but NMDOT could not reimburse until the re-authorized agreement was executed. Reimbursement has been resubmitted to NMDOT | 6/30/2025 | 6/30/2025
Senior Affairs | 2023 | H2011 | Palo Duro Senior Center | PALO DURO SENIOR CTR - REN | 3000000 | 3000000 | 0% | 10/22/24 Received fully executed grant agreement Sept 2024. Conducted community town hall for input, in design phase with Facility Build, DMD PM A. Villanueva. | 6/30/2027 | Received
Senior Affairs | 2024 |  | Palo Duro Senior Center Equipment |  | 40000 | 40000 | Agreement not received from State | 10/25/24 Waiting on state for award letter from ALTSD
Municipal Development | 2023 | H3302 | Palomas Ave. | PALOMAS AVE IMPROVE | 500000 | 406119 | 18.78% | ​In design using part of this funding. Project will commence once design complete. Will go to construction and encumber funds in Summer 2025, due to school request for timing of project. | 6/30/2027 | Received
Municipal Development | 2024 | I3259 | Palomas Ave. | PALOMAS AVE CONSTRUCT | 50000 | 50000 | 0% | ​Agreement received 10/28/24. In design using prior capital outlay funding. Project will commence once design complete. Will go to construction and encumber funds in Summer 2025, due to school request for timing of project. | 6/30/2028 | 10/28/2024
Parks & Recreation | 2022 | G2668 | Parks | ALB DIST 3 PARKS CONSTRUCT | 200000 | 200000 | 0% | NOO expected in December 2024 for playground | 6/30/2026 | 12/29/2022
Parks & Recreation | 2022 | G2718 | Parks | ALB PARKS IMPROVE | 10000 | 271 | 97.29% | Project Complete | 6/30/2026 | 1/10/2023
Parks & Recreation | 2023 | H2858 | Parks Shade Structures | PKS SHADE STRUCTURES IMPROVE | 560000 | 461878 | 17.52% | NOO expected in 2024 for shade structure improvements | 6/30/2027 | 10/11/2023
Parks & Recreation | 2021 | F2637 | Paseo de las Montanas Trail | ALB PASEO DEL LAS MONTANAS TRAIL IMPROVE | 20000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 10/6/2021
Parks & Recreation | 2022 | G2719 | Paseo de las Montanas Trail | ALB PASEO DE LAS MONTANAS TRAIL REPAIR | 26665 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2026 | 1/10/2023
Parks & Recreation | 2023 | H2854 | Paseo de las Montanas Trail | PASEO DE LAS MONTANAS TRAIL IMPROVE | 50000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2027 | 10/11/2023
Municipal Development | 2021 | F2984 | Paseo del Norte | ALB PASEO DEL NORTE EXPAND NORTHWEST EXPAND | 2050000 | 1587432 | 22.56% | ​3 NOO's already issued. Remaining funds to be used for construction pending 11/19/24 bid opening | 6/30/2025 | Received
Municipal Development | 2022 | G3124 | Paseo del Norte | PASEO DEL NORTE & UNSER BLVD EXPAND | 1420000 | 1056857 | 25.57% | Pending bid opening 11/19/24. Project is combined with PdN grants for construction. Unser has federal funds and this grant is being used to satisfy the match requirement for federal funds. | 6/30/2026 | Received
Municipal Development | 2023 | M700126 | Paseo del Norte | Paseo between Kimmick and Rainbow | 3000000 | 3000000 | 0% | Pending bid opening 11/19/24.Project is combined with PdN grants for construction. | 6/30/2027 | Received
Municipal Development | 2023 | H4062 | Paseo del Norte | Paseo del Norte Improvement - Extend Time | 2110864 | 0 | 100% | Awaiting reimbursement from NMDOT. | 6/30/2025 | Received
Municipal Development | 2023 | H3303 | Paseo del Norte | PASEO DEL NORTE BLVD NW EXPAND | 4435000 | 4435000 | 0% | Project short $20M for construction of Phase 2. Pending scope and fee for rights-of-way mapping and acquisition. | 6/30/2027 | Received
Municipal Development | 2024 | I4044 | Paseo del Norte | Paseo del Norte Improvement - Extend Time | 1918000 | 395461.52 | 79.38% | ​Funds originally encumbered under grant E2819; it was reauthorized to extend time under grant I4044. Pending condemnation results to determine future disposition of project requirements. | 6/30/2026 | Received
Municipal Development | 2024 | I3260 | Paseo Del Norte NW & Unser Blvd NW Construct | PASEO DEL NORTE NW & UNSER BLVD NW CONSTRUCT | 2800000 | 2800000 | 0% | ​Pending Bid Opening 11/19/24, these funds will be used either for construction or construction management. NOO to be requested by 12/1/24. | 6/30/2028 | 10/29/2024
Parks & Recreation | 2021 | F2638 | Pat Hurley Park | ALB PAT HURLEY DOG PARK DESIGN | 30000 | 0 | 100% | NOO issued 8/23/24 for design | 6/30/2025 | 10/13/2021
Parks & Recreation | 2022 | G2720 | Petroglyph Estates Park | ALB PETROGLYPH ESTATES PARK REN | 70000 | 0 | 100% | Waiting on State to approve NOO requested in November, 2024 for playground design | 6/30/2026 | 1/10/2023
Parks & Recreation | 2024 | I2785 | Petroglyph Estates Park | PETROGLYPH ESTATES PK IMPROVE | 930000 | 903883 | 2.808% | NOO expected in late 2025 for playground improvements | 6/30/2028 | 8/3/2024
Parks & Recreation - NPO | 2021 | F2640 | Petroglyph Little League | ALB PETROGLYPH LL FCLTY IMPROVE | 30000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 10/6/2021
Parks & Recreation - NPO | 2022 | G2721 | Petroglyph Little League | ALB PETROGLYPH LL REN | 50000 | 0 | 100% | ​Funds fully encumbered. Project currently under construction. Awaiting final invoice. | 6/30/2026 | 1/13/2023
Parks & Recreation - NPO | 2023 | H2856 | Petroglyph Little League | PETROGLYPH LL REN | 140000 | 140000 | 0% | NOO expected in 2025 for next phase field improvements | 6/30/2027 | 10/11/2023
Parks & Recreation | 2023 | H2857 | Phil Chacon Park | PHIL CHACON PK IMPROVE | 127690 | 127690 | 0% | NOO expected in 2025 for 2025 construction | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2786 | Phil Chacon Park | PHIL CHACON PK IMPROVE | 25000 | 25000 | 0% | NOO expected in 2025 for ongoing park renovations | 6/30/2028 | 8/3/2024
Municipal Development | 2023 | H3290 | Princess Jeanne St. | PRINCESS JEANNE STREETS IMPROVE | 75000 | 75000 | 0% | Pending quote from on-call contractor for sidewalk/curb ramp improvements, due 12/31/24. NOO to NMDOT will follow. | 6/30/2027 | 11/6/2023
Municipal Development | 2024 | I4047 | PSD School Crosswalks Reauth | APS School Crosswalks Reauth | 138000 | 138000 | 0% | ​Agreement received 10/28/24 - Pending Quote from striping vendor, anticipated by 12/31/24. Once received NOO to be submitted to NMDOT | 6/30/2026 | 10/28/2024
Municipal Development | 2024 | I3250 | Public Safety Fencing Juan Tabo/I40 Construct | ALB PUB SFTY FENCING JUAN TABO / I-40 CONSTRUCT | 85000 | 85000 | 0% | ​Agreement received 10/28/24, requesting to reauthorize to transfer to NMDOT, since this is specifically for a NMDOT road. | 6/30/2028 | 10/28/2024
Municipal Development | 2022 | G2307 | Pueblo Alto Flood Mitigation | ALB PUEBLO ALTO FLOOD MITIGATION CONSTRUCT | 335000 | 0 | 100% | ​Project delayed due to lack of response from NMED regarding requirements associated with obtaining an NOO. Design underway, estimated design completion 4/30/2025. Project is short $1M for full construction funding. | 6/30/2026 | Received
Municipal Development | 2023 | H2386 | Pueblo Alto Flood Mitigation | PUEBLO ALTO FLOOD MITIGATION IMPROVE | 100000 | 100000 | 0% | Scope and fee for Phase 2 design expected 12/1/24 and NOO to be submitted following receipt. | 6/30/2027 | Received
Municipal Development | 2024 | I3261 | Pueblo Alto/ Mile Hi Flood Mitigation | PUEBLO ALTO/MILE HI STORM WATER INFRA CONSTRUCT | 290000 | 290000 | 0% | ​Agreement received 10/28/24. These funds to be used for final design of phase 2 Scope and fee for final design anticipated 4/30/24 and NOO will be requested after receipt of scope and fee. | 6/30/2028 | 10/28/2024
Parks & Recreation | 2022 | G2728 | Puerto del Sol Golf Course | ALB PUERTO DEL SOL GOLF COURSE IMPROVE | 100000 | 0 | 100% | NOO expected in December 2024 for shade and tee box | 6/30/2026 | 9/7/2022
Parks & Recreation | 2024 | I2794 | Puerto del Sol Golf Course | PUERTO DEL SOL GOLF COURSE DINING CONSTRUCT | 30000 | 30000 | 0% | NOO expected early 2025 for T-box and shade. | 6/30/2028 | 8/3/2024
Parks & Recreation | 2024 | I2795 | Puerto del Sol Golf Course | ALB PUERTO DEL SOL GOLF COURSE IRRIGATION REN | 25000 | 25000 | 0% | NOO expected in 2025 for design for irrigation renovation. | 6/30/2028 | 8/3/2024
Parks & Recreation | 2023 | H2861 | Quigley Park | QUIGLEY PK IMPROVE | 150000 | 50877.31 | 66.08% | NOO issued September 2024 for park improvements | 6/30/2027 | 1/26/2024
Parks & Recreation | 2024 | I2796 | Quintessence Park | QUINTESSENCE PK IRRIGATION REN | 125000 | 125000 | 0% | NOO expected in 2025 for design and 2026 for irrigation improvements | 6/30/2028 | 8/3/2024
Metropolitan Redevelopment | 2023 | H2862 | Rail Trail | RAIL TRAIL CONSTRUCT | 25000 | 0 | 100% | Waiting on DFA to approve NOO for $24,940. Funds encumbered for construction of Sawmill Rail Trail. | 6/30/2027 | 10/11/2023
Metropolitan Redevelopment | 2024 | I2797 | Rail Trail - Barelas Segment | RAIL TRAIL BARELAS CONSTRUCT | 85000 | 85000 | 0% | ​Funding insufficient - Most recent construction cost estimate was over $8M (in 2023). Rail Trail Barelas segment is in the planning stages. Funds will be used to support additional planning needed in the Barelas area, as they are insufficient to cover the cost of construction. | 6/30/2028 | 10/1/2024
Municipal Development | 2024 | M700145 | Rail Trail - Central Crossing | Central crossing rail trail | 10000000 | 10000000 | 0% | ​Design at 95%, construction to begin once completed, which will encumber these funds. | 6/30/2026 | 8/15/2024
Metropolitan Redevelopment | 2024 | I2799 | Rail Trail - Downtown Crossing | ALB RAIL TRAIL DOWNTOWN CROSSING CONSTRUCT | 150000 | 150000 | 0% | ​Project has broken ground. Funds are anticipated to be encumbered soon. | 6/30/2028 | 10/1/2024
Metropolitan Redevelopment | 2024 | I2798 | Rail Trail - Eco and Hispanic Heritage sections | RAIL TRAIL BIOPARK & NATL HISPANIC CULTUAL CTR CONSTRUCT | 25000 | 25000 | 0% | ​Planning is in progress for the segments near the BioPark and the National Hispanic Cultural Center. Additional plans, including traffic studies, will be needed to ensure safe pedestrian and bicycle access at these two points. | 6/30/2028 | 8/3/2024
General Services | 2021 | F2646 | Rail Yards | ALB ABQ RAIL YARDS REN | 230000 | 0 | 100% | ​Project Complete | 6/30/2025 | 10/13/2021
Municipal Development | 2023 | H2863 | Rail Yards | RAIL YARDS HAZ MAT MITIGATE & CORRIDOR REN | 50000 | 0 | 100% | ​Project complete, utilized for contaminated soil removal from railyards. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2022 | G2729 | Recreation Facility | ALB RECREATION FCLTY CONSTRUCT | 20000 | 20000 | 0% | Waiting on APS for Agreement to use property | 6/30/2026 | 2/23/2023
Parks & Recreation | 2024 | I2694 | RECREATIONAL FCLTY CONSTRUCT | RECREATIONAL FCLTY CONSTRUCT | 240000 | 240000 | 0% | Waiting on APS agreement. | 6/30/2028 | 8/23/2024
Parks & Recreation | 2024 | I2803 | Rinconada Dog Park | ALB RINCONADA PARK IMPROVE | 55000 | 55000 | 0% | NOO expected in 2025 for playground improvements | 6/30/2028 | 8/3/2024
Municipal Development | 2024 | I3262 | RIO GRANDE BLVD CONSTRUCT | RIO GRANDE BLVD CONSTRUCT | 250000 | 250000 | 0% | ​Agreement received 10/27/24 - Pending Quote from on-call contractor, requested by 12/31/24. Once received NOO to be submitted to NMDOT | 6/30/2028 | 10/27/2024
Parks & Recreation | 2021 | F2648 | Rio Grande Triangle Dog Park | ALB RIO GRANDE TRIANGLE PARK REN | 30000 | 0 | 100% | ​Project complete. Dog park renovations completed. | 6/30/2025 | 9/22/2021
Parks & Recreation | 2022 | G2615 | Rio Grande Triangle Dog Park | ALB RIO GRANDE TRIANGLE DOG PARK CONSTRUCT | 115000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2026 | 8/29/2022
Parks & Recreation | 2024 | I2805 | Rio Grande Triangle Dog Park | RIO GRANDE TRIANGLE DOG PK IMPROVE | 50000 | 50000 | 0% | NOO expected in 2025 for dog park improvements | 6/30/2028 | 8/3/2024
Health, Housing, & Homelessness - NPO | 2023 | H2814 | Roadrunner Food Bank NPO | EMERGENCY FOOD DISTRIB EQUIP PRCHS | 145000 | 145000 | Agreement not received from State | Waiting on Grant agreements from the State, need to clear Anti-donation rules. | 6/30/2025
Health, Housing, & Homelessness - NPO | 2023 | H4031 | Roadrunner Food Bank NPO | Emergency Food Distribution Program Purchase of Vehicles and Equipment - Extend Time | 87000 | 87000 | 0% | Using State Price agreement to procure vehicle. | 6/30/2025 | 9/15/2023
Health, Housing, & Homelessness - NPO | 2024 | I2742 | Roadrunner Food Bank NPO | ALB FOOD DISTRIB EQUIP PRCHS | 50000 | 50000 | 0% | Using State Price agreement to procure vehicle. | 6/30/2026 | 10/1/2024
Parks & Recreation - NPO | 2023 | H2868 | Roadrunner Little League | ROADRUNNER LL IMPROVE | 113850 | 112980 | 0.7642% | NOO received for parking lot improvements. NOO for remaining funds expected in 2025 for league improvements | 6/30/2027 | 12/7/2023
Parks & Recreation | 2023 | H2869 | Ross Enchanted Park | ROSS ENCHANTED PK IMPROVE | 50000 | 0 | 100% | PROJECT COMPLETE | 6/30/2027 | 11/28/2023
Municipal Development | 2022 | G2732 | Route 66 Celebration | ALB ROUTE 66 CENTENNIAL CELEBRATION DVLP | 25000 | 25000 | 0% | Agreement received 10/24/24 - Quote requested from Vendor, vendor capacity causing delays in providing quote. NOO to be submitted to DFA upon receipt. | 6/30/2026 | 10/24/2024
Arts & Culture | 2023 | H3291 | Route 66 Celebration | ROUTE 66 CENTENNIAL CELEBRATION CONSTRUCT | 50000 | 50000 | 0% | Awaiting quotes from on-call contractor to replace asphalt in west parking lot and related concrete. | 6/30/2027 | Received
Municipal Development | 2023 | H4037 | Route 66 Signage | Route 66 Signage Construction - Extend Time | 50000 | 42500 | 15% | NOO received, NTP issued to vendor. | 6/30/2025 | 9/18/2023
Arts & Culture | 2021 | F2649 | Route 66 Visitor Center | ALB RT 66 VISITOR CTR IMPROVE | 726462 | 466566.08 | 35.78% | Improvements are underway and will be expended to support visitor center exhibit enhancements. | 6/30/2025 | 3/31/2022
Arts & Culture | 2022 | G2733 | Route 66 Visitor Center | ALB ROUTE 66 VISITOR CTR IMPROVE | 999645 | 988936.31 | 1.071% | ​With the Route 66 Center building construction complete, these funds will be used to design and build indoor and outdoor exhibits that engage and educate residents and tourists in the culture, art and history of Route 66. Outdoor exhibits will be focused on walkable sign park with historic, vintage, and commissioned Route 66 and neon signs - this will be a tourist attraction! | 6/30/2026 | 7/3/2024
Arts & Culture | 2023 | H2870 | Route 66 Visitor Center | RT 66 VISITOR CTR IMPROVE | 242550 | 237061.12 | 2.263% | Agreement received 10/11/24 - These funds will be expended when needed site improvements are complete. | 6/30/2027 | 10/11/2024
Arts & Culture | 2024 | I2806 | Route 66 Visitor Center | ROUTE 66 VISITOR CTR IMPROVE | 198000 | 189911.42 | 4.085% | These funds will be expended when needed site improvements are complete. | 6/30/2028 | 8/3/2024
Albuquerque Police Department | 2021 | F2647 | RTCC | ALB REAL TIME CRIME CTR DVLP | 4570000 | 0 | 100% | The City will enter a procurement process in FY25. | 6/30/2025 | 10/6/2021
Albuquerque Police Department | 2024 | I2802 | RTCC | REAL TIME CRIME CTR EXPAND | 630000 | 630000 | 0% | ​Waiting on quotes from RTCC Director. Funds should be encumbered by 12/31/2024. | 6/30/2028 | 9/9/2024
Albuquerque Police Department | 2024 | I2725 | RTCC | REAL TIME CRIME CTR EQUIP | 225000 | 225000 | 0% | NOO pending quotes from vendor | 6/30/2028 | 9/9/2024
Albuquerque Police Department | 2024 | I2734 | RTMC | EMERGENCY OPERATIONS CTR CONSTRUCT | 140000 | 140000 | 0% | Obtaining furniture quote from vendor. | 6/30/2028 | 9/9/2024
Municipal Development | 2024 | I2808 | San Antonio Medians | SAN ANTONIO MEDIAN STUDY PLAN | 50000 | 50000 | 0% | ​Will Reauth in 2025 Leg Session, feasibility study not needed. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2023 | H2872 | San Antonio Oxbow Open Space Poole Property | SAN ANTONIO OXBOW OPEN SPACE IMPROVE | 125000 | 125000 | 0% | NOO expected in early 2025 for Phase 1 improvements and construction. | 6/30/2027 | 2/1/2024
Parks & Recreation | 2024 | I4026 | San Jose Park | San Jose Park | 100000 | 100000 | Agreement not received from State | Awaiting Grant Agreement from DFA – Project currently in design and public outreach phase. Anticipate construction in early 2025 calendar year.
Parks & Recreation | 2024 | I4027 | San Jose Park | ALBUQUERQUE SAN JOSE NEIGHBORHOOD SOUND WALL CONSTRUCTION--CHANGE TO SOUTH SAN JOSE PARK RENOVATION--CHANGE AGENCY--EXTEND TIME--SEVERANCE TAX BONDS. | 560000 | 560000 | Agreement not received from State | Waiting on LGD for Grant Agreement – Project currently in design and public outreach phase. Anticipate construction in 2025 calendar year.
Arts & Culture | 2023 | H2873 | San Pedro Library | SAN PEDRO LIBRARY REN | 149975 | 128668 | 14.21% | Upgrades at the San Pedro Library are underway including HV/AC, roof, interior upgrades, expanded programming space, grounds and landscaping improvements, and security upgrades. This project is in design and full completion is expected in September 2025. | 6/30/2027 | 11/28/2023
Arts & Culture | 2024 | I2809 | San Pedro Library | SAN PEDRO LIB REN | 640000 | 640000 | 0% | This project is in design and full completion is expected in September 2025. | 6/30/2028 | 10/21/2024
Municipal Development | 2024 | I3245 | San Pedro NE Design | SAN PEDRO DR NE STREETSCAPE REN | 800000 | 800000 | 0% | ​Agreement received 10/28/24. Project is completing 30% design using local funds and once design is complete the grant funds to be used for construction. | 6/30/2028 | 10/28/2024
Municipal Development | 2024 | I3263 | Sandia HS Area streets Improve | Sandia HS Area streets Improve | 140000 | 140000 | 0% | ​Agreement received 10/28/24 Traffic safety study underway expected completion 12/31/25 and once design is identified project plans will be developed and capital outlay funds to be used for construction | 6/30/2028 | 10/28/2024
Parks & Recreation | 2021 | F2651 | Sandia Vista Park | ALB SANDIA VISTA DOG PK CONSTRUCT | 20000 | 0 | 100% | Funds fully encumbered for additional work and equipment. | 6/30/2025 | 10/13/2021
Parks & Recreation - NPO | 2021 | F2591 | Santa Barbara Martineztown Community Garden | ALB CMTY GARDEN SANTA BARBARA CONSTRUCT | 60000 | 31167.93 | 48.05% | NOO expected early 2025 for equipment installation for remaining balance. | 6/30/2025 | 8/9/2022
Parks & Recreation | 2022 | G2734 | Santa Barbara Martineztown Community Garden | ALB SANTA BARBARA-MARTINEZTOWN GARDENS DVLP | 200000 | 200000 | Agreement not received from State | Waiting on state for Grant Agreement | 6/30/2026
Parks & Recreation | 2023 | H2847 | Santa Barbara Martineztown Community Garden | MARTINEZTOWN-SANTA BARBARA GARDEN CONSTRUCT | 220000 | 220000 | 0% | Waiting on APS for Agreement to use property | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2771 | Santa Barbara- Martineztown Community Garden | MARTINEZTOWN CMTY GARDEN CONSTRUCT | 100000 | 100000 | 0% | Waiting on APS for use of property | 6/30/2028 | 8/3/2024
Senior Affairs - NPO | 2023 | H2846 | Santa Barbara Martineztown Multigen | MARTINEZTOWN MULTIGENERATIONAL CTR CONSTRUCT | 100000 | 0 | 100% | Project Complete | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2810 | Santa Barbara Park | ALB SANTA BARBARA PARK IMPROVE | 90000 | 90000 | 0% | NOO expected in 2025 for park Improvements | 6/30/2028 | 8/3/2024
Parks & Recreation | 2024 | I2811 | Santa Barbara-Martineztown Park | SANTA BARBARA-MARTINEZTOWN PARK IMPROVE | 150000 | 150000 | 0% | NOO expected in 2025 for park improvements | 6/30/2028 | 8/3/2024
Municipal Development | 2021 | F2973 | Sawmill & 12th St. | 12TH ST NW AND SAWMILL RD NW IMPROVE ALB | 300000 | 13285 | 95.57% | ​Project is in design. Project will be phased due to lack of full funding. Full project is short funding $1.5M. Final design for phased project expected 3/15/25 | 6/30/2025 | Received
Municipal Development | 2022 | G3083 | Sawmill & 12th St. | 12TH ST & SAWMILL RD CONSTRUCT | 548000 | 261284 | 52.32% | ​Funds are partially encumbered. Since appropriations received to date are insufficient to construct the planned improvements and scope and fee has been requested to developed a phasing plan for the planned improvements and expected 12/15/24. Once received an NOO for that work will be requested from NMDOT. Project is $1.5M short for full funding | 6/30/2026 | Received
Municipal Development | 2023 | H3286 | Sawmill & 12th St. | 12TH ST AND BELLAMAH AVE IMPROVE | 250000 | 250000 | 0% | Project is in design using previously encumbered appropriations. Scope and fee requested to develop a construction phasing plan and expected by 12/15/24 to design improvements using currently available funding. Appropriations received to date are not sufficient to construct the needed improvements. Project is short $1.5M for full construction funding. | 6/30/2027 | Received
Municipal Development | 2024 | I3231 | Sawmill & 12th St. | 12TH ST AND SAWMILL RD CONSTRUCTION | 350000 | 350000 | 0% | ​Funds are not sufficient to construct the improvements, project short $1.5M to complete entire project. Working on phasing plan to utilize available funding now. | 6/30/2028 | 10/28/2024
Municipal Development | 2021 | F2652 | Sawmill & Oldtown Pedestrian Safety | ALB SAWMILL/OLD TOWN PEDESTRIAN STREET CONSTRUCT | 1385000 | 0 | 100% | ​Used for design. Construction to be complete by 10/1/2025 | 6/30/2025 | 10/28/2021
Municipal Development | 2022 | G3110 | Sawmill & Oldtown Pedestrian Safety | ALB SAWMILL & OLD TOWN ST & PED RT IMPROVE | 10605000 | 221572 | 97.91% | ​NOO issued, project in construction with an estimated completion of January 2026. | 6/30/2026 | 6/3/2023
Municipal Development | 2023 | H3293 | Sawmill & Oldtown Pedestrian Safety | SAWMILL & OLD TOWN PEDESTRIAN SAFETY IMPROVE | 525000 | 0 | 100% | ​NOO issued, project in construction with an estimated completion of January 2026. | 6/30/2027 | Received
Metropolitan Redevelopment - NPO | 2022 | G2735 | Sawmill SLC NPO | ALB SAWMILL CMTY LAND TRUST PLAZA REN | 200000 | 200000 | 0% | ​Reauthorizing in 2025 Leg Session, project as scoped cannot meet anti-donation. | 6/30/2026 | 2/9/2023
Arts & Culture | 2021 | F2639 | Sawmill Visual Arts | ALB PERFORMING,VISUAL ARTS, ED CENTER PREP | 1127027 | 1127027 | Agreement not received from State | Waiting on the State, as the agreement has not been released as of 10/25/24. Initial correspondence was sent on 5/24/24, followed by multiple follow-ups to expedite the process. | 6/30/2025
Arts & Culture | 2022 | G2723 | Sawmill Visual Arts | ALB PRF VISUAL ARTS ED CTR PREP | 1766000 | 1735865 | 1.706% | Awaiting State’s release of funds pending for full encumbrance. A city-owned site has been identified. | 6/30/2026 | 7/5/2024
Arts & Culture | 2023 | H2855 | Sawmill Visual Arts | PERFORMING ARTS & ED CTR CONSTRUCT | 2900000 | 2900000 | Agreement not received from State | ​Waiting on the State, as the agreement has not been released as of 10/25/24. Initial correspondence was sent on 5/24/24, followed by multiple follow-ups to expedite the process. | 6/30/2027
Parks & Recreation | 2024 | I2813 | Shade Structures in Six Parks | ALB SHADE STRUCT PK CONSTRUCT | 40000 | 40000 | 0% | NOO expected in 2025 for shade structures | 6/30/2028 | 8/3/2024
Parks & Recreation | 2021 | F2654 | Shooting Range Park | ALB SHOOTING RANGE PARK & APD TRAINING CTR CONSTRU | 100000 | 50.53 | 99.95% | PROJECT COMPLETE | 6/30/2025 | 11/1/2021
Parks & Recreation | 2022 | G2738 | Shooting Range Park | ALB SHOOTING RANGE PK UPGRADE | 130000 | 0 | 100% | ​ Grant fully expended and project completed. | 6/30/2026 | 9/7/2022
Parks & Recreation | 2023 | H2876 | Shooting Range Park | SHOOTING RANGE PK IMPROVE | 150000 | 150000 | 0% | NOO expected in early 2025 for archery range improvements | 6/30/2027 | 11/29/2023
Parks & Recreation | 2024 | I2814 | Shooting Range Park | SHOOTING RANGE PK IMPROVE | 100000 | 100000 | 0% | NOO expected in 2025 for infrastructure | 6/30/2028 | 8/3/2024
Parks & Recreation | 2021 | F2655 | Sierra Vista Pool | ALB SIERRA VISTA SWIM AND TENNIS FCLTY IMPROVE | 50000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 10/28/2021
Municipal Development | 2021 | F2985 | Silver & Lead | SILVER AVE AND LEAD AVE IMPROVE | 60000 | 0 | 100% | ​Project completed. | 6/30/2025 | Received
Parks & Recreation | 2021 | F2656 | Singing Arrow Open Space | ALB SINGING ARROW ARCHAEOLOGICAL SITE IMPROVE | 120000 | 0 | 100% | Grant fully expended and completed. | 6/30/2025 | 11/1/2021
Parks & Recreation | 2023 | H2877 | Singing Arrow Park | SINGING ARROW PK IMPROVE | 150000 | 0 | 100% | Project will be fully encumbered pending NOO approval with state. Used for playground renovation. | 6/30/2027 | 1/26/2024
Arts & Culture | 2023 | H2878 | South Broadway Library | SOUTH BROADWAY LIBRARY REN | 206910 | 119599 | 42.2% | Currently obtaining quotes for furniture and blinds. | 6/30/2027 | 12/8/2023
Arts & Culture | 2024 | I2815 | South Broadway Library | SOUTH BROADWAY LIB REN | 55000 | 55000 | 0% | ​Currently obtaining quotes for furniture and blinds. | 6/30/2028 | 10/21/2024
Parks & Recreation | 2023 | H2871 | South San Jose Park | S SAN JOSE PK EXPAND & IMPROVE | 150000 | 150000 | 0% | NOO expected in late 2025/early 2026 for park renovation | 6/30/2027 | 1/26/2024
Parks & Recreation | 2024 | I2816 | South San Jose Park | ALB SOUTH SAN JOSE PK IMPROVE | 450000 | 450000 | 0% | NOO expected in 2025 for park renovations | 6/30/2028 | 8/21/2024
Arts & Culture | 2024 | I2817 | South Valley Library | ALB SOUTH VALLEY LIB FURNISH | 25000 | 25000 | 0% | Planning is underway for upgrades, to begin once quotes are received. | 6/30/2028 | 10/1/2024
Albuquerque Police Department | 2023 | H2875 | Southeast Area Command - Phil Chacon | SE AREA APD FCLTYS CONSTRUCT | 1485000 | 785000 | 47.14% | Construction 84% complete. | 6/30/2027 | 11/28/2023
Municipal Development | 2022 | G3111 | Southeast Intersections | ALB SE ALBUQUERQUE INTRSECT ACCESS IMPROVE | 50000 | 50000 | 0% | ​Quote requested for equipment, due by 12/1/24. NOO to follow receipt. | 6/30/2026 | Received
Albuquerque Police Department | 2024 | I2820 | Southwest Area Command | ALB SW POLICE STN CONSTRUCT | 50000 | 50000 | 0% | ​Newly awarded funds. Planning is in progress. | 6/30/2028 | 9/9/2024
Municipal Development | 2023 | H3294 | Southwest Medians | SW MESA MEDIAN LANDSCAPING CONSTRUCT | 50000 | 50000 | 0% | ​Pending quote from contractor, anticipated receipt 12/1/24. NOO to NMDOT to follow. | 6/30/2027 | Received
Parks & Recreation | 2023 | H2881 | Southwest Mesa Parks | SW MESA PARKS CONSTRUCT | 20000 | 506.58 | 97.47% | NOO expected 2025 for playground | 6/30/2027 | 11/28/2023
Parks & Recreation | 2024 | I2818 | Southwest Mesa Parks | LB SW MESA & S VALLEY PK CONSTRUCT | 100000 | 100000 | 0% | NOO expected in 2025 for park improvements | 6/30/2028 | 8/21/2024
Municipal Development | 2024 | I2819 | Southwest Mesa Street Lights Install | ALB SW MESA ST LIGHT INSTALL | 50000 | 50000 | 0% | Quote expected 12/31/24, NOO will be sent to NMDOT following receipt of quote. | 6/30/2028 | 10/1/2024
Albuquerque Fire Rescue | 2021 | F2659 | Southwest Public Safety Center - Fire Station 23 | ALB SW PUB SFTY CTR CONSTRUCT | 55000 | 0 | 100% | ​Project complete. Funding used for Fire Station 23. | 6/30/2025 | 10/28/2021
Albuquerque Fire Rescue | 2022 | G2616 | Southwest Public Safety Center - Fire Station 23 | ALB SW MESA PUB SFTY & CMTY CMPLX CONSTRUCT | 350000 | 68490.83 | 80.43% | ​Use for SW mesa public safety FS 23. $ $342,056.81 obligated $ 266,522.97 reimbursements submitted but not yet received. | 6/30/2026 | 12/29/2022
Albuquerque Fire Rescue | 2022 | G2740 | Southwest Public Safety Center - Fire Station 23 | ALB SOUTHWEST PUBLIC SAFETY CTR CONSTRUCT | 50000 | 0 | 100% | ​Project complete. Funding used for SW Public Safety Center Fire Station 23 | 6/30/2026 | 1/13/2023
Albuquerque Police Department | 2023 | H2879 | Southwest Public Safety Center - Fire Station 23 | SOUTHWEST PUBLIC SAFETY CTR PLAN | 2985000 | 0 | 100% | Fully encumbered | 6/30/2027 | 11/28/2023
Albuquerque Fire Rescue | 2024 | I2821 | Southwest Public Safety Center - Fire Station 23 | SW PUB SFTY CTR CONSTRUCT | 1683000 | 1271124.33 | 24.47% | Southwest Public Safety Center/Fire Station 23 - Phase 1 under construction, estimated completion in August 2025. | 6/30/2028 | 8/3/2024
Municipal Development | 2023 | H4039 | Southwest Street Lights | Southwest Mesa Street Light Construction - Extend Time | 308672 | 308672 | 0% | Finalizing lighting plans. NOO to NMDOT to follow. | 6/30/2025 | Received
Municipal Development | 2023 | H3295 | Southwest Street Lights | SW MESA STREET LIGHTS INSTALL | 50000 | 50000 | 0% | ​Pending quote from lighting contractor, anticipated receipt 12/31/24, NOO to NMDOT to follow. | 6/30/2027 | Received
Municipal Development | 2022 | G3107 | Southwest Street Lights | ALB DIST 3 STREET LIGHTS INSTALL | 100000 | 100000 | 0% | ​Scope and fee anticipated 12/31/24, NOO to NMDOT to follow. | 6/30/2026 | Received
Arts & Culture | 2021 | F2657 | Special Collections Library | ALB RPLC LIB ROOF Special Collections HVAC REN | 60000 | 0 | 100% | ​Roof repairs are completed. All funds are expended. | 6/30/2025 | 10/28/2021
Arts & Culture | 2022 | G2724 | Special Collections Library | ALB PUB LIB SPECIAL COLLECTIONS BRANCH REN | 100000 | 53569.87 | 46.43% | The project is underway and expected to be complete by the end of January 2025. | 6/30/2026 | 1/17/2023
Parks & Recreation | 2022 | G2667 | Splashpads | ALB DIST 1 SPLASH PADS CONSTRUCT | 1000000 | 909477 | 9.052% | Waiting on APS for Agreement for use of land. | 6/30/2026 | 1/6/2023
Municipal Development - NPO | 2023 | H2864 | Steam Locomotive | RAIL YARDS INFRA & TURNTABLE REN | 475000 | 475000 | Agreement not received from State | ​Waiting on Grant Agreement from LGD, will be used by Rio Metro/MRCOG. | 6/30/2027
Municipal Development - NPO | 2024 | I2847 | Steam Locomotive | Railyards improve infrastructure | 200000 | 200000 | Agreement not received from State | ​Waiting on Grant Agreement from LGD | 6/30/2028
Municipal Development | 2022 | G2736 | Streets | ALB SD 16 STREETS & SAFETY IMPROVE | 300000 | 46278.23 | 84.57% | Used for minor street and sidewalk projects, remainder using by 12/15/24 for speedbumps. | 6/30/2026 | 9/7/2022
Municipal Development | 2022 | G3108 | Streets | ALB CITY COUNCIL DIST 9 STREETS IMPROVE | 200000 | 200000 | 0% | ​Pending contractor quote for pavement rehab, due by 12/15/2024. NOO from NMDOT to follow. | 6/30/2026 | Received
Arts & Culture - NPO | 2023 | H2880 | Suicide Memorial | SUICIDE MEM CONSTRUCT | 225000 | 225000 | Agreement not received from State | Pending input from group, Public Arts Division to issue RFP for project management and design services | 6/30/2027
Health, Housing, & Homelessness - NPO | 2024 | I4028 | Surgical center | ALB SURGICAL & INTEGRATED CARE CTR CONSTRUCT, RET | 2450000 | 2450000 | 0% | Awaiting non-profit's scope of services for Use Agreement to meet Anti-Donation. | 6/30/2027 | 10/24/2024
Arts & Culture | 2021 | F2660 | Taylor Ranch Library | ALB TAYLOR RANCH LIBRARY REN | 400000 | 0 | 100% | Project currently in progress. Funds fully spent on Taylor Ranch library reroof and HVAC. | 6/30/2025 | 10/28/2021
Arts & Culture | 2023 | H2882 | Taylor Ranch Library | TAYLOR RANCH LIBRARY REN | 523800 | 0 | 100% | These funds will be utilized for upgrades and renovation following the replacement of the lower roof and HVAC, funded with an earlier grant. | 6/30/2027 | 10/11/2023
Arts & Culture | 2024 | I2822 | Taylor Ranch Library | TAYLOR RANCH LIB IMPROVE | 100000 | 100000 | 0% | Along with 2023 grant, these funds will be expended on the subsequent phase of construction once previous phase is complete. | 6/30/2028 | 10/1/2024
Arts & Culture | 2024 | I4029 | Taylor Ranch Library | Taylor Ranch Library | 100000 | 100000 | 0% | Along with 2023 grant, these funds will be expended on the subsequent phase of construction once previous phase is complete. | 6/30/2026 | 11/8/2024
Arts & Culture - NPO | 2023 | H4034 | Three Sisters NPO | Food Business Incubator and Kitchen Construction - Extend Time | 287100 | 287100 | 0% | Waiting on TSK to determine which location, and will purchase equipment once NPO determines location selection | 6/30/2025 | 9/18/2023
Arts & Culture - NPO | 2024 | I2832 | Three Sisters NPO | ALB VEH & TEACHING KITCHEN EQUIP | 20000 | 20000 | 0% | Waiting on TSK to determine which location, and will purchase equipment once NPO determines location selection | 6/30/2026 | 10/1/2024
Arts & Culture - NPO | 2024 | I4015 | Three Sisters NPO | ALBUQUERQUE BUSINESS INCUBATOR AND KITCHEN CONSTRUCTION, EXTEND TIME, SEVERANCE TAX BONDS | 122265 | 122265 | 0% | Waiting on TSK to determine which location, and will purchase equipment once NPO determines location selection | 6/30/2026 | 11/8/2024
Parks & Recreation | 2024 | I2723 | Thunderbird LL | COMANCHE N & S PK IMPROVE | 50000 | 50000 | 0% | NOO expected in 2025 for league improvements | 6/30/2028 | 8/20/2024
Parks & Recreation | 2024 | I2824 | Tijeras Arroyo Biozone Education Improve | ALB TIJERAS ARROYO BIOZONE ED FCLTY IMPROVE | 125000 | 125000 | 0% | NOO expected in 2025 for design and 2026 for improvements to the Open Space | 6/30/2028 | 8/21/2024
Parks & Recreation | 2022 | G2743 | Tijeras BioZone | ALB TIJERAS BIO-ZONE OPEN SPC AC | 100000 | 0 | 100% | PROJECT COMPLETE | 6/30/2026 | 8/29/2022
Arts & Culture | 2022 | G2744 | Tingley Beach | ALB TINGLEY BEACH WATER SYS & BATHRM IMPROVE | 102171 | 102171 | 0% | These funds will be used for the installation of the USS Albuquerque. | 6/30/2026 | 1/10/2023
Parks & Recreation | 2021 | F2586 | Tom Bolack Park Upgrade & Bike Trail | ALB BIKE TRAIL TOM BOLACK PARK EXPAND | 50000 | 0 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 9/22/2021
Arts & Culture | 2021 | F2661 | Tony Hillerman Library | ALB RPLC LIB Tony Hillerman PKG LOT CONSTRUCT | 50000 | 7939 | 84.12% | ​This project is underway and completion is expected in 2025. | 6/30/2025 | 10/28/2021
Arts & Culture | 2022 | G2684 | Tony Hillerman Library | ALB HILLERMAN LIB PKG LOT RPLC | 275000 | 275000 | 0% | 100% of construction documents received. Awaiting Quote from Contractor. | 6/30/2026 | 12/29/2022
Arts & Culture | 2023 | H2885 | Tony Hillerman Library | TONY HILLERMAN LIBRARY SECURITY SYS INSTALL | 100000 | 33976 | 66.02% | Project is underway and completion is expected by the end of January 2025. | 6/30/2025 | 10/11/2023
Arts & Culture | 2024 | I2825 | Tony Hillerman Library | TONY HILLERMAN LIB REN | 594000 | 594000 | 0% | Pending scope and fees, NoO will be submitted | 6/30/2028 | 10/1/2024
Parks & Recreation | 2022 | G3105 | Tramway Landscaping | TRAMWAY BLVD IMPROVE | 250000 | 250000 | 0% | ​Waiting on NM DOT permit and Agreement. | 6/30/2026 | 11/29/2022
Parks & Recreation | 2022 | G3125 | Tramway Landscaping | TRAMWAY RD LNDSCP REN | 700000 | 347294.46 | 50.39% | ​Waiting on NMDOT to use remaining funds. | 6/30/2026 | 11/29/2022
Parks & Recreation | 2023 | H2886 | Tramway Landscaping | TRAMWAY BLVD LNDSCP IMPROVE | 125000 | 125000 | 0% | Waiting on NM DOT. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2827 | Tramway Landscaping | ALB TRAMWAY BLVD LNDSCP IMPROVE | 150000 | 150000 | 0% | ​NOO expected in 2025 for streetscape improvements | 6/30/2028 | 10/1/2024
Parks & Recreation | 2021 | F2662 | Trumbull Park | ALB TRUMBULL PK REN | 150000 | 106567.93 | 28.95% | ​NOO expected in 2025 for playground renovation | 6/30/2025 | 10/28/2021
ABQ Ride/Transit | 2024 | I2828 | Uptown Connect | UPTOWN HSING CONSTRUCT | 50000 | 50000 | 0% | Awaiting scope and fee from vendor for project planning & design, NOO to encumber will follow receipt. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2023 | H2888 | USS Albuquerque | USS ALBUQUERQUE PARK INSTALL | 50000 | 0 | 100% | Funds fully encumbered. Used to restore USS ABQ. | 6/30/2027 | 10/11/2023
Parks & Recreation | 2022 | G2745 | USS Bullhead Park | ALB USS BULLHEAD MEM PARK/DOG PARK IMPROVE | 50000 | 0 | 100% | ​Project complete. Dog park renovations complete. | 6/30/2026 | 8/29/2022
Parks & Recreation | 2023 | H2889 | USS Bullhead Park | USS BULLHEAD MEM PK IMPROVE | 200000 | 200000 | 0% | ​NOO expected for 2025 for construction late 2025/early 2026 | 6/30/2027 | 1/26/2024
Parks & Recreation | 2024 | I2830 | USS Bullhead Park | USS BULLHEAD MEM PK IMPROVE | 100000 | 100000 | 0% | ​NOO expected in 2025 for additional design and 2026 for infrastructure improvements | 6/30/2028 | 8/21/2024
Albuquerque Police Department | 2023 | H2890 | Valley Police Station | VALLEY AREA POLICE STN REN | 150000 | 0 | 100% | Fully encumbered | 6/30/2027 | 10/11/2023
Parks & Recreation | 2024 | I2831 | Valley Pool | VALLEY POOL REN | 230000 | 230000 | 0% | ​NOO expected in 2025 for pool improvements | 6/30/2028 | 8/21/2024
Parks & Recreation | 2021 | F2663 | Ventana Ranch Sports Office | ALB VENTANA RANCH PARK SPORTS OFC CONSTRUCT | 50000 | 0 | 100% | ​Project complete. Improved Ventana Ranch park sports office. | 6/30/2025 | 10/28/2021
Parks & Recreation | 2022 | G2746 | Ventana Ranch Sports Office | ALB VENTANA RANCH PARK TENNIS COURT CMPLX DVLP | 50000 | 0 | 100% | ​Project complete. Improvements made at Ventana Ranch Park tennis courts. | 6/30/2026 | 1/10/2023
Parks & Recreation | 2024 | I2780 | Vista Allegre Trail / North Rinconada Trail | NORTH RINCONADA TRAIL CONSTRUCT | 345000 | 345000 | 0% | ​NOO expected in 2025 for design and 2026 for trail improvements | 6/30/2028 | 10/1/2024
Parks & Recreation | 2024 | I2835 | Vista del Norte Drive NE Trail | VISTA DEL NORTE TRAIL REN | 100000 | 100000 | 0% | ​NOO expected in 2025 for trail design. | 6/30/2028 | 8/21/2024
Parks & Recreation | 2022 | G2747 | Vista del Norte Park | ALB VISTA DEL NORTE PARK IMPROVE | 225000 | 0 | 100% | NOO issued October 2024. Completion of the restrooms will be in 2025 | 6/30/2026 | 1/10/2023
Parks & Recreation | 2023 | H2891 | Vista del Norte Park | VISTA DEL NORTE PK IMPROVE | 148500 | 142350 | 4.141% | ​NOO expected in 2025 for park improvements. Remaining balance to be used for Nature Play. | 6/30/2027 | 10/19/2023
Parks & Recreation | 2024 | I2834 | Vista Del Norte Park | ALB VISTA DEL NORTE PK CONSTRUCT | 100000 | 100000 | 0% | ​NOO expected in 2025 for nature play improvements | 6/30/2028 | 8/21/2024
Parks & Recreation | 2021 | F2664 | Wellesley Park | ALB WELLESLEY PK TENNIS COURTS REN | 40000 | 0 | 100% | ​Project complete. Project to recoat the tennis courts at Wellesley Park. | 6/30/2025 | 10/28/2021
Parks & Recreation | 2024 | I2838 | Wells Park | ALB WELLS PK EQUIP | 50000 | 50000 | 0% | ​NOO expected in 2025 for active and ongoing park renovations | 6/30/2028 | 8/23/2024
Arts & Culture - NPO | 2024 | I2793 | WESST NPO | PROFESSIONAL SOUND STUDIO CONSTRUCT | 1190000 | 1190000 | 0% | Use Agreement has been drafted and is under currently under review. Once approved, the use agreement will be sent to the State for approval. | 6/30/2028 | 10/1/2024
Metropolitan Redevelopment | 2022 | G4028 | West Central MRA | WEST CENTRAL METROPOLITAN REDEVELOPMENT IMPROVEMENTS | 38800 | 734 | 98.11% | ​This project is completed. The funds were utilized to upgrade storage facilities at Westside Animal Shelter. | 6/30/2026 | 8/9/2022
Parks & Recreation | 2022 | G2748 | West Mesa Aquatic Center | ALB WEST MESA AQUATIC CTR IMPROVE | 50000 | 60.44 | 99.88% | ​Project complete. Utilized for improvements at West Mesa aquatic center. | 6/30/2026 | 8/29/2022
Parks & Recreation - NPO | 2021 | F2678 | West Mesa Little League | WEST MESA LL FCLTY IMPROVE | 127000 | 0.01 | 100% | ​PROJECT COMPLETE | 6/30/2025 | 11/5/2021
Parks & Recreation - NPO | 2022 | G2749 | West Mesa Little League | ALB WEST MESA LL FCLTY IMPROVE | 50000 | 0 | 100% | NOO obtained 2024. Construction in progress. Completion expected 2025. | 6/30/2026 | 1/11/2023
Parks & Recreation - NPO | 2023 | H2866 | West Mesa Little League | REDLANDS PK W MESA LL IMPROVE | 170000 | 0 | 100% | NOO Obtained 2024. Construction in progress. Completion expected early 2025. | 6/30/2027 | 12/8/2023
Parks & Recreation | 2024 | I2836 | West Mesa Trails Plan | ALB W MESA TRAIL PLAN CONSTRUCT | 40000 | 40000 | 0% | ​NOO expected in 2025 for construction. | 6/30/2028 | 8/21/2024
Youth & Family Services | 2021 | F2665 | Westgate Community Center | ALB WESTGATE CMTY CTR REN | 143000 | 0 | 100% | Construction completion May 2024 | 6/30/2025 | 10/28/2021
Youth & Family Services | 2021 | F2666 | Westgate Community Center | ALB WESTGATE COMMUNITY CTR CONSTRUCT | 250000 | 0 | 100% | Construction completion May 2024 | 6/30/2025 | 10/28/2021
Youth & Family Services | 2022 | G2750 | Westgate Community Center | ALB WESTGATE CMTY CTR | 5207400 | 0 | 100% | Community Center construction completion May 2024 | 6/30/2026 | 9/7/2022
Youth & Family Services | 2023 | H2893 | Westgate Community Center Gym | WESTGATE CMTY CTR CONSTRUCT | 257400 | 257400 | 0% | Funding is short $7 million for construction of the new gymnasium | 6/30/2027 | 10/11/2023
Youth & Family Services | 2024 | I2840 | Westgate Community Center Gym | WESTGATE CMTY CTR PH 3 CONSTRUCT | 345000 | 345000 | 0% | Funding is short $7 million for construction of the new gymnasium | 6/30/2028 | 9/6/2024
Parks & Recreation - NPO | 2022 | G2751 | Westgate Little League | ALB WESTGATE LL FIELD IMPROVE | 100000 | 100000 | 0% | NOO expected in December 2024. | 6/30/2026 | 1/10/2023
Parks & Recreation | 2024 | I2826 | Westgate Little League | TOWER POND & WESTGATE HEIGHTS PKS IMPROVE | 150000 | 150000 | 0% | ​NOO expected in 2025 for league improvements | 6/30/2028 | 8/21/2024
Animal Welfare | 2022 | G2752 | Westside Animal Shelter | ALB WESTSIDE ANIMAL SHELTER IMPROVE | 30000 | 0 | 100% | Project complete. Used to improve outdoor spaces and Westside animal shelter. | 6/30/2026 | 1/10/2023
Animal Welfare | 2023 | H2895 | Westside Animal Shelter | WESTSIDE ANIMAL SHELTER KENNELS & VET CLINIC C | 355000 | 355000 | 0% | ​Project is in design. Funding will be used for construction services. | 6/30/2027 | 10/11/2023
Animal Welfare | 2023 | H2894 | Westside & Eastside Shelter | WESTSIDE & EASTSIDE ANIMAL SHELTERS IMPROVE | 1480001 | 1480001 | 0% | ​Currently in design. Funding will be used for construction. | 6/30/2027 | 10/11/2023
Animal Welfare | 2024 | I2837 | Westside Animal Shelter | ALB W SIDE ANIMAL SHELTER REN | 250000 | 250000 | 0% | Project in design, funding will be used for construction. | 6/30/2028 | 9/6/2024
Municipal Development | 2023 | H4046 | Westside Arterials | Westside Arterial Route Improvement - Extend Time | 693639 | 12621 | 98.18% | Several reimbursements still pending payment with NMDOT. Delay in getting grant agreement for reauthorization delayed reimbursement process. Expenses being incurred for design efforts on various projects. | 6/30/2027 | 2/2024
Parks & Recreation | 2023 | H4029 | Westside Indoor Sports Complex | West Side Sports Complex Construction - Extend Time | 1787874 | 1732927.55 | 3.073% | ​Waiting on agreement with land owner. NOO expected 2025. | 6/30/2027 | 9/18/2023
Parks & Recreation | 2024 | I2841 | Westside Indoor Sports Complex | WESTSIDE INDOOR SPORTS CMPLX CONSTRUCT | 25000 | 25000 | 0% | ​Waiting on agreement with land owner. | 6/30/2028 | 8/23/2024
Parks & Recreation | 2024 | I4020 | Westside Indoor Sports Complex | ALBUQUERQUE WEST SIDE INDOOR SPORTS FACILITY CONSTRUCTION--CHANGE TO INDOOR SPORTS COMPLEX--EXTEND TIME--SEVERANCE TAX BONDS.-- | 297000 | 297000 | 0% | ​Waiting on agreement with land owner. NOO expected 2025. | 6/30/2026 | 8/23/2024
Parks & Recreation | 2024 | I4021 | Westside Indoor Sports Complex | Westside Indoor Sports Complex | 1732928 | 1732928 | 0% | ​Waiting on agreement with land owner. NOO expected 2025. | 6/30/2026 | 8/23/2024
Parks & Recreation | 2024 | I4022 | Westside Indoor Sports Complex | ALBUQUERQUE WEST SIDE INDOOR RECREATION COMPLEX CONSTRUCTION--CHANGE TO INDOOR SPORTS COMPLEX IMPROVEMENT--EXTEND TIME--SEVERANCE TAX BONDS.-- | 198000 | 198000 | 0% | ​Waiting on agreement with land owner. NOO expected 2025. | 6/30/2026 | 8/23/2024
Parks & Recreation | 2024 | I4031 | Westside Indoor Sports Complex | Westside Indoor Sports Complex | 887755 | 887755 | 0% | ​Waiting on agreement with land owner. NOO expected 2025. | 6/30/2026 | 8/23/2024
Parks & Recreation | 2022 | G2754 | Westside Pickleball | ALB WESTSIDE PICKLEBALL COURTS CONSTRUCT | 125000 | 125000 | 0% | ​NOO expected November 2024 for construction. | 6/30/2026 | 1/10/2023
Parks & Recreation | 2024 | I4030 | Westside Spraypad | Westside Spraypad | 445500 | 445500 | 0% | ​Waiting on APS Agreement for use of their land | 6/30/2027 | 8/23/2024
Municipal Development - NPO | 2021 | F2668 | Wheels Museum | ALB WHEELS MUSEUM IMPROVE | 75000 | 841 | 98.88% | Project Complete | 6/30/2025 | 7/18/2022
Municipal Development - NPO | 2022 | G2617 | Wheels Museum | ALB WHEELS MUSEUM FCLTY IMPROVE | 100000 | 100000 | 0% | Agreement received from state 12/5/24, routing for signatures. | 6/30/2026 | 12/5/2024
Municipal Development - NPO | 2023 | H2865 | Wheels Museum | RAILYARDS WHEELS MUSEUM TRACK REPAIR | 225000 | 7220.81 | 96.79% | ​Project under construction with Rio Metro/MRCOG | 6/30/2027 | 10/11/2024
Municipal Development - NPO | 2023 | H2896 | Wheels Museum | WHEELS MUS ACCESSIBILITY IMPROVE | 197450 | 197450 | Agreement not received from State | ​Waiting on Grant Agreement from LGD | 6/30/2027
Municipal Development - NPO | 2024 | I2801 | Wheels Museum | RAILROAD MUSEUM IMPROVE | 70000 | 70000 | 0% | Coordinating with NPO to determine use, NPO desires feasibility study, but building has a leak that needs funds more. | 6/30/2028 | 10/1/2024
Parks & Recreation | 2024 | I2842 | Wilson Pool Building Improvements | WILSON POOL BLDG REN | 275000 | 261942.81 | 4.748% | ​NOO expected in 2025 for pool improvements | 6/30/2028 | 10/1/2024
Parks & Recreation | 2024 | I2843 | Worker's Memorial Park Plan | ALB WORKER'S MEM PK IMPROVE | 75000 | 75000 | 0% | ​NOO expected in 2025 for design | 6/30/2028 | 8/23/2024
Health, Housing, & Homelessness - NPO | 2022 | G2756 | YDI NPO | ALB YOUTH FCLTY PRCHS | 585000 | 585000 | Agreement not received from State | Waiting for Grant Agreement from LGD - Waiting for Environmental assessment and surveys of Flora Vista property. Accumulating funds for large building purchase. | 6/30/2026
Health, Housing, & Homelessness - NPO | 2023 | H2900 | YDI NPO | YOUTH SVCS & TRANSITIONAL HSING FCLTY CONSTRUC | 766490 | 766490 | Agreement not received from State | Waiting on the State for Grant Agreement - Waiting for Environmental assessment and surveys of Flora Vista property. Accumulating funds for large building purchase. | 6/30/2027
Health, Housing, & Homelessness - NPO | 2024 | I2728 | YDI NPO | ALB EARLY CHILDHOOD ED FCLTY PRCHS | 230000 | 230000 | 0% | Waiting for Environmental assessment and surveys of Flora Vista property. Accumulating funds for large building purchase. | 6/30/2028 | 9/6/2024
Health, Housing, & Homelessness - NPO | 2024 | I4032 | YDI NPO | YDI NPO | 144045 | 144045 | 0% | ​Waiting for Environmental assessment and surveys of Flora Vista property. Accumulating funds for large building purchase. | 6/30/2026 | 9/6/2024
Municipal Development | 2024 | I3264 | Young Ave Construct | Young Avenue | 160000 | 3242 | 97.97% | ​Agreement received 10/28/24. NOO submitted to NMDOT. | 6/30/2028 | 10/28/2024
Parks & Recreation - NPO | 2023 | H2901 | Zia Little League | ZIA LL PK IMPROVE | 80000 | 58867.62 | 26.42% | 2nd NOO will be obtained in 2025 for remaining improvements. | 6/30/2027 | 11/28/2023